## Project Tracking List
PMO WEBSITE HIGH LEVEL PROJECT TRACKING LIST
Updated: 11/21/13
Item | Sub Task | Task | Status | Notes | Target Start | Target Completion | Actual Completion | Person Responsible
HOME PAGE CONTENT
1 | 0 | Inventory of current PMO website content
| 1 | Decide which content to keep and no longer include in the new website | Complete | 10/17: Team decided to remove a couple of tabs and consolidate content in some. | 2013-10-07 | 2013-10-17 | 2013-10-17 | Team
| 2 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
2 | 0 | Home Page Templates
| 1 | Team to decide the kind of information that needs to be placed in the new website templates | Complete |  | 2013-10-07 | 2013-10-07 | 2013-10-07 | Team
| 2 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
3 | 0 | Site background
| 1 | Team to pick from background options | Complete |  | 2013-10-07 | 2013-10-07 | 2013-10-07 | RR; Team
| 2 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
4 | 0 | Site image
| 1 | Find out cost of purchasing stock photos and schedule photo shoot for creating an in-house image as Plan B. | Complete | 10/24: Team decided to purchase stock photo for home page. Roni to cancel photo shoot and send photo options to Michelle for final review. | 2013-10-18 | 2013-10-24 | 2013-10-24 | RR
| 2 | Final approval | In Progress | 10/24: Michelle to let Roni know which stock photos to purchase. | 2013-10-24 | 2013-11-06 |  | MD
| 3 | Order photos and upload into T4 | Not yet started |  | 2013-11-21 | 2013-11-21 | 2013-11-21 | RR
| 4 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
5 | 0 | Home Page: Contact Us (same content as ECM website's LUC's ECM Team)
| 1 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
6 | 0 | Home Page: PM Request Form
| 1 | Team review of introductory text | Complete |  | 2013-10-17 | 2013-10-24 | 2013-10-24 | Team
| 2 | PM Request Form - Word document version | In Progress | 10/24: Michelle to get final approval from Jim. | 2013-10-24 | 2013-11-06 |  | MD
| 3 | Send approved version to Roni | Not yet started |  | 2013-10-24 | 2013-11-21 |  | MD
| 4 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 5 | Request and obtain eForm version from Katherine | Not yet started |  | 2013-11-22 | 2013-12-02 |  | RR; KK
| 6 | Review eForm version | Not yet started |  | 2013-12-02 | 2013-12-02 |  | RR
| 7 | Team review of eForm version | Not yet started |  | 2013-12-02 | 2013-12-02 |  | Team
| 8 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
7 | 0 | Home Page: About the PMO
| 1 | Draft "About the PMO" section in home page | Complete |  | 2013-10-25 | 2013-10-25 | 2013-10-27 | RR
| 2 | Team review | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 3 | Make revisions | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | RR
| 4 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
8 | 0 | Home Page: News
| 1 | Research PM Articles | Complete |  | 2013-10-18 | 2013-10-24 | 2013-10-24 | RR
| 2 | Obtain permissions | Complete |  | 2013-10-18 | 2013-10-24 | 2013-10-24 | RR
| 3 | Team review | Complete | 11/6: Team has decided to pass on articles from other PM websites and wait for PMI's permission to use their articles. | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 4 | Ask for permission to link to PMI website | Complete |  | 2013-10-21 | 2013-10-21 | 2013-10-21 | RR
| 5 | Obtain permission to link to PMI website | In Progress |  | 2013-11-20 | 2013-11-20 |  | PMI
| 6 | Ask for permission to use PMI articles | In Progress |  | 2013-10-17 | 2013-11-06 |  | HT
| 7 | Obtain permission to use PMI articles | In Progress |  | 2013-11-20 | 2013-11-20 |  | PMI
| 7 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
9 | 0 | Home Page: Quick Links to Popular Project Management and Quality Assurance Templates
| 1 | Decide which templates to include in this section | Complete |  | 2013-10-08 | 2013-10-17 | 2013-10-17 | Team
| 2 | Draft Template 1_Meeting Agenda Example | Complete |  | 2013-10-24 | 2013-10-24 | 2013-10-24 | RR
| 3 | Team review | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 4 | Make revisions | Complete |  | 2013-10-25 | 2013-10-25 | 2013-10-25 | RR
| 5 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 6 | Draft Template 2_Meeting Summary Example | Complete |  | 2013-10-22 | 2013-10-22 | 2013-10-24 | RR
| 7 | Team review | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 8 | Make revisions | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | RR
| 9 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 10 | Draft Template 3_Project Checklist Example | Not yet started |  |  |  |  | RR
| 11 | Team review | Not yet started |  |  |  |  | Team
| 12 | Make revisions | Not yet started |  |  |  |  | RR
| 13 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 14 | Draft Template 4_Project Definition Example | Not yet started |  |  |  |  | RR
| 15 | Team review | Not yet started |  |  |  |  | Team
| 16 | Make revisions | Not yet started |  |  |  |  | RR
| 17 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 18 | Draft Template 5_Project Feedback Example | Not yet started |  |  |  |  | RR
| 19 | Team review | Not yet started |  |  |  |  | Team
| 20 | Make revisions | Not yet started |  |  |  |  | RR
| 21 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 22 | Draft Template 6_Risk Management Matrix Example | Not yet started |  |  |  |  | RR
| 23 | Team review | Not yet started |  |  |  |  | Team
| 24 | Make revisions | Not yet started |  |  |  |  | RR
| 25 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 26 | Draft Template 7_Tracking List v1 Example | Complete |  | 2013-10-25 | 2013-11-06 | 2013-11-06 | RR
| 27 | Team review | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 28 | Make revisions | In Progress |  | 2013-11-07 | 2013-11-20 | 2013-11-21 | RR
| 29 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
| 30 | Draft Template 8_Tracking List v2 Example | Not yet started |  |  |  |  | RR
| 31 | Team review | Not yet started |  |  |  |  | Team
| 32 | Make revisions | Not yet started |  |  |  |  | RR
| 33 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
10 | 0 | Home Page: PMO Metrics
| 1 | Draft content | Complete |  | 2013-10-17 | 2013-10-17 | 2013-10-17 | RR
| 2 | Update "Active LUC PMO Projects" PDF document | Complete |  | 2013-10-24 | 2013-10-24 | 2013-10-24 | RR
| 3 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
TAB 1: ABOUT THE PMO
1 | 0 | Mission & Vision - Description + Diagram
| 1 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
2 | 0 | Project Management Life Cycle Diagram
| 1 | The Value of Project Management | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Issues Implementing Project Management | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Project Roles and Responsibilities | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
3 | 0 | Quality Assurance Life Cycle Diagram
| 1 | What can QA do for you? | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Top 10 QA Testing Tips | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | QA Process Instructions | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
4 | 0 | FAQ Document
| 1 | Brainstorm with team | Not yet started |  |  |  |  | Team
| 2 | Draft FAQ document | Not yet started |  |  |  |  | RR
| 3 | Team review | Not yet started |  |  |  |  | Team
| 4 | Make revisions | Not yet started |  |  |  |  | RR
| 5 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
5 | 0 | Staff Directory (same content as Home Page: Contact Us)
| 1 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
6 | 0 | PM Request Form (same content as Home Page: PM Request Form)
| 1 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
TAB 2: PROJECT MANAGEMENT TEMPLATES
1 | 0 | Recommended Project Management Templates
| 1 | Initiation Phase: Project Checklist | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Initiation Phase: Project Definition | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Initiation Phase: Functional Specs Doc | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Planning Phase: Risk Management | Complete |  | N/A | N/A | N/A | N/A - existing content
| 5 | Planning Phase: Communication Plan | Complete |  | N/A | N/A | N/A | N/A - existing content
| 6 | Execution Phase: Status Report | Complete |  | N/A | N/A | N/A | N/A - existing content
| 7 | Execution Phase: Defect Log Template | Complete |  | N/A | N/A | N/A | N/A - existing content
| 8 | Closeout Phase: Closeout Meeting Agenda | Complete |  | N/A | N/A | N/A | N/A - existing content
| 9 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13
2 | 0 | Suggested Project Management Templates
| 1 | Initiation Phase: Initiation Phase Agenda | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Initiation Phase: Sponsor Feedback Form | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Planning Phase: Advanced Risk Management | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Planning Phase: Planning Phase Kickoff Agenda | Complete |  | N/A | N/A | N/A | N/A - existing content
| 5 | Planning Phase: Project Contact List | Complete |  | N/A | N/A | N/A | N/A - existing content
| 6 | Execution Phase: Execution Phase Kickoff Agenda | Complete |  | N/A | N/A | N/A | N/A - existing content
| 7 | Closeout Phase: Project Closure Report | Complete |  | N/A | N/A | N/A | N/A - existing content
| 8 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
3 | 0 | Supplemental Project Management Templates
| 1 | Initiation Phase: Staffing Commitment | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Initiation Phase: Initial Project Plan | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Initiation Phase: Initiation Phase Review | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Initiation Phase: Project Kickoff Presentation | Complete |  | N/A | N/A | N/A | N/A - existing content
| 5 | Initiation Phase: Project Roles and Responsibilities | Complete |  | N/A | N/A | N/A | N/A - existing content
| 6 | Planning Phase: Work Breakdown Structure | Complete |  | N/A | N/A | N/A | N/A - existing content
| 7 | Planning Phase: Comprehensive Project Plan | Complete |  | N/A | N/A | N/A | N/A - existing content
| 8 | Planning Phase: Planning Phase Review | Complete |  | N/A | N/A | N/A | N/A - existing content
| 9 | Execution Phase: Deliverable Acceptance Form | Complete |  | N/A | N/A | N/A | N/A - existing content
| 10 | Execution Phase: Project Acceptance Form | Complete |  | N/A | N/A | N/A | N/A - existing content
| 11 | Execution Phase: Execution Phase Review | Complete |  | N/A | N/A | N/A | N/A - existing content
| 12 | Closeout Phase: Project Feedback | Complete |  | N/A | N/A | N/A | N/A - existing content
| 13 | Closeout Phase: Process Modification Recommendation | Complete |  | N/A | N/A | N/A | N/A - existing content
| 14 | Closeout Phase: Closeout Phase Review | Complete |  | N/A | N/A | N/A | N/A - existing content
| 15 | Closeout Phase: Project Closeout Presentation | Complete |  | N/A | N/A | N/A | N/A - existing content
| 16 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13
TAB 3: QUALITY ASSURANCE TEMPLATES
1 | 0 | Recommended Quality Assurance Templates
| 1 | Use Case Scenarios | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Test Script Template | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
2 | 0 | Suggested Quality Assurance Templates
| 1 | Mantis Issue Tracking | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Mantis User Documentation | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13
TAB 4: REPORTING AND SCHEDULING TEMPLATES
1 | 0 | Reporting and Scheduling Templates
| 1 | Status Report Template | Complete |  | N/A | N/A | N/A | N/A - existing content
| 2 | Meeting Agenda | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Executive Status Document | Complete |  | N/A | N/A | N/A | N/A - existing content
| 4 | Meeting Summary | Complete |  | N/A | N/A | N/A | N/A - existing content
| 5 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
TAB 5: RESOURCES
1 | 0 | Additional Reading
| 1 | Same content posted in "Home Page: News" section | In Progress |  | 2013-10-18 | 2013-11-21 |  | HT
| 2 | Article archives (articles included in old PMO website) | Complete |  | N/A | N/A | N/A | N/A - existing content
| 3 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
2 | 0 | Links to other Project Management websites
| 1 | Decide which PM websites to link to | Complete |  | 2013-11-06 | 2013-11-06 | 2013-11-06 | Team
| 2 | Upload into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
TECHNICAL ITEMS
1 | 0 | Uploading all approved content into T4
| 1 | Request new templates from Bob | Not yet started |  | 2013-11-21 | 2013-11-21 |  | RR
| 2 | Ask Bob to create KeyMatch terms in Google Appliance so that if you search for PMO on the local (LUC) Google search, it will be at the top of the results | Not yet started |  | 2013-11-21 | 2013-11-21 |  | RR
| 3 | Upload all content into T4 | Not yet started |  | 2013-12-09 | 2013-12-13 |  | RR
2 | 0 | Final approval
| 1 | Team review with Jim | Not yet started |  | 2013-12-18 | 2013-12-18 |  | Team
| 2 | Make final revisions | Not yet started |  | 2013-12-19 | 2013-12-20 |  | RR
| 3 | Update T4 | Not yet started |  | 2013-12-20 | 2013-12-20 |  | RR
| 4 | Go-Live | Not yet started |  | 2013-12-23 | 2013-12-23 |  | BK; RR
ON-GOING UPDATES/WEBSITE MAINTENANCE
1 | 0 | Home Page: News
| 1 | Research PM Articles | Not yet started | 10/24: To be updated quarterly | 2014-04-01 | 2014-04-04 |  | RR
| 2 | Obtain permissions | Not yet started |  | 2014-04-15 | 2014-04-18 |  | RR; PMI
| 3 | Team review | Not yet started |  | 2013-04-22 | 2013-04-22 |  | Team
| 4 | Upload into T4 | Not yet started |  | 2014-04-23 | 2013-04-23 |  | RR
2 | 0 | Home Page: PMO Metrics
| 1 | Update Metrics spreadsheet | Not yet started | 10/24: To be updated quarterly | 2014-04-01 | 2014-04-01 |  | RR
| 2 | Update "Active LUC PMO Projects" PDF document | Not yet started |  | 2014-04-01 | 2014-04-01 |  | RR
| 3 | Upload into T4 | Not yet started |  | 2014-04-01 | 2014-04-01 |  | RR
KEY
In Progress
Completed or Removed
Not yet started
On Hold