## Overview
Owner |  | Submit Date | Target Date | Status | Notes
HOME PAGE
Inventory of current PMO website content
Team | Decide which content to keep and no longer include in the new website | 2013-10-07 | 2013-10-17 | Completed | 10/17: Team decided to remove a couple of tabs and consolidate content in some.
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page Templates
Team | Team to decide the kind of information that needs to be placed in the new website templates | 2013-10-07 | 2013-10-07 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Site background
RR; Team | Team to pick from background options | 2013-10-07 | 2013-10-07 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Site image
RR | Find out cost of purchasing stock photos and schedule photo shoot for creating an in-house image as Plan B. | 2013-10-18 | 2013-10-24 | Completed | 10/24: Team decided to purchase stock photo for home page. Roni to cancel photo shoot and send photo options to Michelle for final review.
MD | Final approval | 2013-10-24 | 2013-11-06 | In Progress | 10/24: Michelle to let Roni know which stock photos to purchase.
RR | Order photos and upload into T4 | 2013-11-21 | 2013-11-21 | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page: Contact Us (same content as ECM website's LUC's ECM Team)
RR | Upload into T4 | 2013-12-09 | 2013-12-13
Home Page: PM Request Form
Team | Team review of introductory text | 2013-10-17 | 2013-10-24 | Completed
MD | PM Request Form - Word document version | 2013-10-24 | 2013-11-06 | In Progress | 10/24: Michelle to get final approval from Jim.
MD | Send approved version to Roni | 2013-10-24 | 2013-11-21 | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR; KK | Request and obtain eForm version from Katherine | 2013-11-22 | 2013-12-02 | Not Yet Started
RR | Review eForm version | 2013-12-02 | 2013-12-02 | Not Yet Started
Team | Team review of eForm version | 2013-12-02 | 2013-12-02 | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page: About the PMO
RR | Draft "About the PMO" section in home page | 2013-10-25 | 2013-10-25 | Completed
Team | Team review | 2013-11-06 | 2013-11-06 | Completed
RR | Make revisions | 2013-11-06 | 2013-11-06 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page: News
RR | Research PM Articles | 2013-10-18 | 2013-10-24 | Completed
RR | Obtain permissions | 2013-10-18 | 2013-10-24 | Completed
Team | Team review | 2013-11-06 | 2013-11-06 | In Progress | 11/6: Team has decided to pass on articles from other PM websites and wait for PMI's permission to use their articles.
RR | Ask for permission to link to PMI website | 2013-10-21 | 2013-10-21 | Completed
PMI | Obtain permission to link to PMI website | 2013-11-20 | 2013-11-20 | In Progress
HT | Ask for permission to use PMI articles | 2013-10-17 | 2013-11-06 | In Progress
PMI | Obtain permission to use PMI articles | 2013-11-20 | 2013-11-20 | In Progress
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page: Quick Links to Popular Project Management and Quality Assurance Templates
Team | Decide which templates to include in this section | 2013-10-08 | 2013-10-17 | Completed
RR | Draft Template 1_Meeting Agenda Example | 2013-10-24 | 2013-10-24 | Completed
Team | Team review | 2013-11-06 | 2013-11-06 | Completed
RR | Make revisions | 2013-10-25 | 2013-10-25 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 2_Meeting Summary Example | 2013-10-22 | 2013-10-22 | Completed
Team | Team review | 2013-11-06 | 2013-11-06 | Completed
RR | Make revisions | 2013-11-06 | 2013-11-06 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 3_Project Checklist Example |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 4_Project Definition Example |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 5_Project Feedback Example |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 6_Risk Management Matrix Example |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 7_Tracking List v1 Example | 2013-10-25 | 2013-11-06 | Completed
Team | Team review | 2013-11-06 | 2013-11-06 | Completed
RR | Make revisions | 2013-11-07 | 2013-11-20 | In Progress
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
RR | Draft Template 8_Tracking List v2 Example |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Home Page: PMO Metrics
RR | Draft content | 2013-10-17 | 2013-10-17 | Completed
RR | Update "Active LUC PMO Projects" PDF document | 2013-10-24 | 2013-10-24 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TAB 1: ABOUT THE PMO
Mission & Vision - Description + Diagram
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Project Management Life Cycle Diagram
N/A - existing content | The Value of Project Management | N/A | N/A | Completed
N/A - existing content | Issues Implementing Project Management | N/A | N/A | Completed
N/A - existing content | Project Roles and Responsibilities | N/A | N/A | Completed
| Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Quality Assurance Life Cycle Diagram
N/A - existing content | What can QA do for you? | N/A | N/A | Completed
N/A - existing content | Top 10 QA Testing Tips | N/A | N/A | Completed
N/A - existing content | QA Process Instructions | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
FAQ Document
Team | Brainstorm with team |  |  | Not Yet Started
RR | Draft FAQ document |  |  | Not Yet Started
Team | Team review |  |  | Not Yet Started
RR | Make revisions |  |  | Not Yet Started
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Staff Directory (same content as Home Page: Contact Us)
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
PM Request Form (same content as Home Page: PM Request Form)
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TAB 2: PROJECT MANAGEMENT TEMPLATES
Recommended Project Management Templates
N/A - existing content | Initiation Phase: Project Checklist | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Project Definition | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Functional Specs Doc | N/A | N/A | Completed
N/A - existing content | Planning Phase: Risk Management | N/A | N/A | Completed
N/A - existing content | Planning Phase: Communication Plan | N/A | N/A | Completed
N/A - existing content | Execution Phase: Status Report | N/A | N/A | Completed
N/A - existing content | Execution Phase: Defect Log Template | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Closeout Meeting Agenda | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Suggested Project Management Templates
N/A - existing content | Initiation Phase: Initiation Phase Agenda | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Sponsor Feedback Form | N/A | N/A | Completed
N/A - existing content | Planning Phase: Advanced Risk Management | N/A | N/A | Completed
N/A - existing content | Planning Phase: Planning Phase Kickoff Agenda | N/A | N/A | Completed
N/A - existing content | Planning Phase: Project Contact List | N/A | N/A | Completed
N/A - existing content | Execution Phase: Execution Phase Kickoff Agenda | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Project Closure Report | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Supplemental Project Management Templates
N/A - existing content | Initiation Phase: Staffing Commitment | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Initial Project Plan | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Initiation Phase Review | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Project Kickoff Presentation | N/A | N/A | Completed
N/A - existing content | Initiation Phase: Project Roles and Responsibilities | N/A | N/A | Completed
N/A - existing content | Planning Phase: Work Breakdown Structure | N/A | N/A | Completed
N/A - existing content | Planning Phase: Comprehensive Project Plan | N/A | N/A | Completed
N/A - existing content | Planning Phase: Planning Phase Review | N/A | N/A | Completed
N/A - existing content | Execution Phase: Deliverable Acceptance Form | N/A | N/A | Completed
N/A - existing content | Execution Phase: Project Acceptance Form | N/A | N/A | Completed
N/A - existing content | Execution Phase: Execution Phase Review | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Project Feedback | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Process Modification Recommendation | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Closeout Phase Review | N/A | N/A | Completed
N/A - existing content | Closeout Phase: Project Closeout Presentation | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TAB 3: QUALITY ASSURANCE TEMPLATES
Recommended Quality Assurance Templates
N/A - existing content | Use Case Scenarios | N/A | N/A | Completed
N/A - existing content | Test Script Template | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Suggested Quality Assurance Templates
N/A - existing content | Mantis Issue Tracking | N/A | N/A | Completed
N/A - existing content | Mantis User Documentation | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TAB 4: REPORTING AND SCHEDULING TEMPLATES
Reporting and Scheduling Templates
N/A - existing content | Status Report Template | N/A | N/A | Completed
N/A - existing content | Meeting Agenda | N/A | N/A | Completed
N/A - existing content | Executive Status Document | N/A | N/A | Completed
N/A - existing content | Meeting Summary | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TAB 5: RESOURCES
Additional Reading
HT | Same content posted in "Home Page: News" section | 2013-10-18 | 2013-11-21 | In Progress
N/A - existing content | Article archives (articles included in old PMO website) | N/A | N/A | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Links to other Project Management websites
Team | Decide which PM websites to link to | 2013-11-06 | 2013-11-06 | Completed
RR | Upload into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
TECHNICAL ITEMS
Uploading all approved content into T4
RR | Request new templates from Bob | 2013-11-21 | 2013-11-21 | Not Yet Started
RR | Ask Bob to create KeyMatch terms in Google Appliance so that if you search for PMO on the local (LUC) Google search, it will be at the top of the results | 2013-11-21 | 2013-11-21 | Not Yet Started
RR | Upload all content into T4 | 2013-12-09 | 2013-12-13 | Not Yet Started
Final approval
Team | Team review with Jim | 2013-12-18 | 2013-12-18 | Not Yet Started
RR | Make final revisions | 2013-12-19 | 2013-12-20 | Not Yet Started
RR | Update T4 | 2013-12-20 | 2013-12-20 | Not Yet Started
BK; RR | Go-Live | 2013-12-23 | 2013-12-23 | Not Yet Started
ON-GOING UPDATES/WEBSITE MAINTENANCE
Home Page: News
RR | Research PM Articles | 2014-04-01 | 2014-04-04 | On Hold | 10/24: To be updated quarterly
RR; PMI | Obtain permissions | 2014-04-15 | 2014-04-18 | On Hold
Team | Team review | 2013-04-22 | 2013-04-22 | On Hold
RR | Upload into T4 | 2014-04-23 | 2013-04-23 | On Hold
Home Page: PMO Metrics
RR | Update Metrics spreadsheet | 2014-04-01 | 2014-04-01 | On Hold | 10/24: To be updated quarterly
RR | Update "Active LUC PMO Projects" PDF document | 2014-04-01 | 2014-04-01 | On Hold
RR | Upload into T4 | 2014-04-01 | 2014-04-01 | On Hold
KEY
Not Yet Started
In Progress
On Hold
Completed