## Prioritization Instructions
ITESC "Top 20" Prioritization Exercise
Desired Outcome:
► Identify the top technology projects for the university that best fit the qualifying characteristics based on the LUC strategic plan and goals
► Whittle down the list of projects "in-progress" to a manageable number and/or set appropriate expectations with regard to delivery dates
► Focus ITS resources on these projects
► Proactively manage resourcing issues in conjunction with the project capacity/availability of the organization
► Reset role expectations for project sponsors and project team members
Instructions:
► Reminder: 1) Project groupings for dependent or related projects ("Program Name" in column D) will receive one ranking.
However, projects within a single Program may have different priorities and delivery dates assigned and will be resourced accordingly.
2) Project sizing estimates using the "T-Shirt" method has been provided in column I for all projects.
X-Small = < 5 days, Small = 5-30 days, Medium = 31-60 days, Large = 61-120 Days, X-Large > 120 Days
3) Institutional Impact Statements are provided in column F on the Prioritization Worksheet.
► Each area represented on the IT Executive Steering Committee will submit one ranking sheet (1-20) of the top priority projects
For example, we'll receive one sheet from Finance, Human Resources, Development, Facilities, Academic Affairs, Student Affairs, and ITS.
► The "Prioritization Worksheet" tab within this spreadsheet will be used for this exercise. Using column G, "Your Ranking", rank your
projects from 1 to 20, where 1 is the most important. Do not rank the mandatory projects as work must be executed to support
standard institutional processes; they are sorted to the top of the list for your reference only.
► For your convenience, the projects already rated "high" by the Project Review Board are included in the Prioritization Worksheet tab,
as well as the new projects that have been submitted/requested since we developed the last Plan of Record.
We anticipate that the PRB has done a pretty good job of identifying the top projects and therefore, most of your top items will already be listed here.
Prior ITESC rankings are also shown in column H for your reference.
► The complete list of 147 projects is in the "FY09 Q1-Q2 Plan Of Record" tab, sorted by Priority (A=High, B=Medium, C=Low, M=Mandatory)
It is recommended that each committee member performs a cursory review of the B and C projects for prioritization consideration.
If you identify a B or C project that should be incorporated into your Top 20 ranking, please add it on one of the five blank lines at the
bottom of the Prioritization Worksheet. Column B ,"Row Nbr", will assist with moving between the 2 sheets.
► The list of the 52 completed is in the "FY08 Q3-Q4 Completed" tab, sorted by Priority.
Next Steps:
► Prioritized Worksheets are Due By: June 30th, 2008
► Submissions will be consolidated and reviewed at the July 2008 ITESC meeting
► Questions can be directed to Susan Malisch, 8-7750 or Jim Sibenaller, 8-7665

## Prioritization Worksheet
Pri | Row Nbr | PSS Nbr | Program Group | Project Desc | Institutional Impact Statement | Your Ranking | Prior Ranking | T-Shirt Sizing | Status | Est. Compl. (QTR) | Primary Customer
M | 1 |  | 4-Construction Projects | Construction Initiatives: - Ignatius House | Mandated. In support of facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q1 | Facilities
M | 2 |  | 4-Construction Projects | Construction Initiatives: - Cudahy Library | Install wireless connectivty to Echo Room | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 3 |  | 4-Construction Projects | Construction Initiatives: - Crown Center | Remodel CC 114/115 to an Electroinc classroom only | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 4 |  | 4-Construction Projects | Construction Initiatives: - Sullivan Center | Remodeling and moving of staff in Sullivan center | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 5 |  | 4-Construction Projects | Construction Initiatives: - Bus Shelter | Equip new bus shelter with technology | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 6 |  | 4-Construction Projects | Construction Initiatives: - Santa Clara Remodeling | Mandated. In support of academic and facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q1 | Facilities
M | 7 |  | 4-Construction Projects | Construction Initiatives: - Sullivan Center | Equip Galvin Auditorium with technology | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 8 |  | 4-Construction Projects | Construction Initiatives: - Mertz Hall | Remodel old east west lounge for staff | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 9 |  | 4-Construction Projects | Construction Initiatives: - New Dorm's online - Le Moyne, Canisius at LSC | Mandated. In support of academic and facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q1 | Facilities
M | 10 |  | 4-Construction Projects | Construction Initiatives: - The Clare - Infrastructure Design and Budgeting | Mandated. In support of academic and facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q2 | Facilities
M | 11 |  | 4-Construction Projects | WTC Data Center Remediation | Current data center lacks proper environmental services. This project will address required cooling and power needs. | N/A | Not Previously Ranked | Large | Active | Q2 | Information Technology Services
M | 12 |  | 4-Construction Projects | Construction Initiatives: - Crown Center Lower level | Upon relocation of servers remodel space for modern languages | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 13 |  | 4-Construction Projects | Construction Initiatives: - Sullivan Center | CAS to Sullivan | N/A | Not Previously Ranked | Small | Pending | Q4+ | Facilities
M | 14 |  | 4-Construction Projects | Construction Initiatives: - Granada Center | School of Nursing to Granada | N/A | Not Previously Ranked | Medium | Pending | Q4+ | Facilities
M | 15 |  | 4-Construction Projects | Construction Initiatives: - Coffey Hall remodeling | Entire building being remodeled | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 16 |  | 4-Construction Projects | Construction Initiatives: - VSTC | Addition on to Gentile for Varsity sports | N/A | Not Previously Ranked | Medium | Active | Q4+ | Facilities
M | 17 |  | 4-Construction Projects | Construction Initiatives: - Faculty / Staff lounge | New faculty staff lounge adjacent to Cudahy Science | N/A | Not Previously Ranked | Medium | Active | Q4+ | Facilities
M | 18 |  | 4-Construction Projects | Construction Initiatives: - 20-24 Chicago Ave. | New building on Chicago Avenue attached to 25 E | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 19 |  | 4-Construction Projects | Construction Initiatives: - Mundelein – Infrastructure Design & Implementation Multi - phased. | Mandated. In support of academic and facilities initiatives. | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 20 |  | 4-Construction Projects | Construction Initiatives: - 25 E law School Multi phased | Lewis Library and Law School Library are switching locations | N/A | Not Previously Ranked | Large | Active | Q4+ | Facilities
M | 21 |  | 4-Construction Projects | Construction Initiatives: - Burrowes House for Provost and President | Remodel the old Yellow house. | N/A | Not Previously Ranked | Medium | Pending | Q3 | Facilities
M | 22 |  | 4-Construction Projects | Remodel LT 16 / 17 | Mandated. In support of administration and facilities initiatives. | N/A | Not Previously Ranked | Medium | Hold | Q4+ | Facilities
M | 23 |  | 5-Security Projects | PCI/DSS Compliance | Compliance to the PCI/DSS standard is mandatory. Failure to comply with the standard can result in significant fines and a critical risk from a PR perspective. Additionally, if a breach of credit card data occurs while Loyola is non-compliant, Loyola would be forced to comply as a Level 1 merchant in addition to a multitude of additional fines. Total costs for such noncompliance or a breach could be significant. | N/A | Not Previously Ranked | X-Large | Active | Q4 | Finance
M | 24 |  |  | Create Electronic space in Echo Room of Cudahy Library | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | N/A | Not Previously Ranked | Small | Active | Q1 | Academic Affairs
M | 25 |  |  | Security Initiative | Implement a Wide area emergency broadcast system via an announcement to emergency phones strategically locate4d on campus | N/A | Not Previously Ranked | Small | Active | Q1 | Facilities
M | 26 |  |  | Add Display to IC Reading Room | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | N/A | Not Previously Ranked | Small | Active | Q1 | Academic Affairs
M | 27 |  |  | Provide Technology in LUMA @ WTC | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | N/A | Not Previously Ranked | Small | Active | Q1 | Academic Affairs
M | 28 |  |  | Create Electronic space on 4th Floor of Information Commons | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | N/A | Not Previously Ranked | Medium | Active | Q2 | Academic Affairs
A | 29 | 739 | 1-Student System Upgrade | Upgrade RDS to PeopleSoft 9.0 Tables The RDS will be upgraded to extract data from PeopleSoft 9.0. | Maintain functionality of the student reporting database (RDS) after LOCUS upgrade until a more permanent solution is implemented. |  | 1 | Medium | Active | Q1 | Academic Affairs
A | 30 | 667 | 1-Student System Upgrade | LOCUS Campus Solutions 9.0 upgrade | Continuation of support and regulatory updates for LOCUS after current support ends on 8/31/2007. Required step of the SIS upgrade. |  |  | X-Large | Active | Q1 | AA-Office of the Provost
A | 32 | 320 | 3-LOCUS Enhancements | LOCUS Enhancements: - Self Service Apply for Graduation | Unify disparate school graduation applications to support self service for students applying for graduation. |  | 2 | Small | Hold | Q1 | AA-Registration & Records
A | 33 | 640 | 3-LOCUS Enhancements | LOCUS Enhancements: Requested Rooms report over time by department | Provides the ability to review trends in academic space utilization. |  |  | Small | Active | Q1 | AA-Registration & Records
A | 34 | 319 | 3-LOCUS Enhancements | LOCUS Enhancements: - Grade Change process | Automate grade change process for routine grade changes submitted by faculty. |  |  | Medium | Hold | Q1 | AA-Registration & Records
A | 35 | 632 | 3-LOCUS Enhancements | LOCUS Enhancements: Correcting unpaid balance on Self-Service Make A Payment page. | Clarify balance due related to unapplied credits. |  |  | Medium | Active | Q1 | Finance
A | 48 | 32 | 3-LOCUS Enhancements | Implement collections module within the student system | Currently the Busar staff use excel list from the Collectors report.Any updates to a student account are done manually. Utilization of the Collectors Module should streamline the process, improve workflow and communication with staff.Bottom line impact should be a reduced accounts receivables and fewer acctounts turned over to collection agencys |  |  | Small | Active | Q1 | Finance
A | 36 | 641 | 3-LOCUS Enhancements | Load Previous Education to LOCUS from Grad R-Plus | Enhance preparation of commencement program & enhance student record completeness. |  |  | Large | Active | Q2 | AA-Registration & Records
A | 37 | 727 | 3-LOCUS Enhancements | A report that shows the results of each night's Tuition Calculation results. | Report used to identify students that are charged incorrectly, will eliminate student complaints |  |  | Small | Active | Q2 | General Accounting
A | 38 | 439 | 3-LOCUS Enhancements | LOCUS Enhancements: - Load AP/MDT test results to LOCUS, post to student records, in an automated (timely) fashion to assist Admissions Advisement. | Automate currently manual processes of acquiring external placement/credit test results from authorized testing vendors. |  |  | Small | Active | Q2 | AA-Enrollment Management
A | 39 | 568 | 3-LOCUS Enhancements | Debug Account Audit Statement | Improve useability of Account Audit Statement report. |  |  | Large | Active | Q2 | Finance
A | 56 | 799 | 3-LOCUS Enhancements | Update IPEDS Reporting | Changes are needed to support the new IPEDS requirements. IPEDS now requires universities to report further detail on race and ethnicity. Data collection points such as applications will need to be altered as well as R+ appion and interface, SIS and associated reports. |  |  | Large | Pending | Q2 | AA-Registration & Records
A | 40 |  | 5-Security Projects | Personal Information Risk Group (PIRG) Policy Implementation | Create and implement the required policies, supporting procedures and training to protect and govern personally identifiable information (PII). The policies and processes are required to enable institutional governance. Not implementing will result in an increased risk to the unwanted exposure of PII. |  | 3 | Large | Active | Q2 | Office of the President
A | 41 |  | 5-Security Projects | Personal Information Risk Group (PIRG) Disk Encryption Rollout | Identify and implement the necessary software, supporting procedures and training to identify and encrypt personally identifiable information (PII). Not implementing the software and corresponding procedures will result in an increased risk to the unwanted exposure of PII. |  |  | Large | Active | Q2 | Office of the President
A | 42 | 423 | 5-Security Projects | Blackboard Campus Card - switch from Social Security Number to LID as the primary key within the Blackboard database. | Reduce security risks with Personal Information by removing SSN from the Campus Card system. |  |  | Medium | Active | Q2 | FN-Campus Card
A | 43 | 635 | 8-Advancement | Upgrade Advancement databases to 10g | Required first step to upgrade the Advancement application (see PSS 325,339). Additionally, the upgrade of the database to 10g provides more robust database tools fr performance tuning and maintenance. |  | 7 | Medium | Active | Q2 | Advancement
A | 44 | 325, 339 | 8-Advancement | Upgrade BSR/SmartCall to new release | New functions allow gathering more specific information on donors so as to better target fund raising efforts. Security of the application is greatly enhanced. Additional functionality in the areas of Cell Phone Management, Allocation Tracking, Gift Processing, Email address consolidation and provides the ability to have release note access |  |  | Large | Active | Q2 | Advancement
A | 57 | 735 |  | This project will investigate, select, and implement an upgrade from our current Unix based Blackboard Transaction System to a system based on the windows operating system and a supported database. From the SSR: "Upgrade the existing Campus Card transaction system to a windows-based system. This upgrade will provide a more user-friendly application and provide many potential savings... | Enhance Campus Card functionality including: - improved process for issuing cards - point of sale transaction flow - interfaces with other systems such as RMS meal plans and MAXXESS security - improved reporting; and - easier maintenance. |  | 8 | Large | Active | Q4 | Finance
A | 54 | 709 |  | This is the next phase of IDM3. The immediate need is to provide SSOM University employees the ability to authenticate to University resources to administer their own benefits. The secondary need is to uniquely identify all Loyola employees (Hospital and University) so that we might identify and use the same UVID on either side of Loyola. The SST stands for Shared Source of Truth. | Provide a share database that will allow LUMC and LUC to verify uvid, reducing redundancy and conflicts. Provides a method to streamline access to shared resources. |  | 13 | Large | Active | Q2 | Human Resources
A | 52 | 762 |  | Messaging and Information Lists | There is a need to be able to easily create email lists for targeted groups such as faculty, staff or students taking into consideration each individuals status and then sending the email. Consideration must be given to the abiliy to break these groups down into smaller targeted groups such as: 'all currently enrolled students in the business school that live in the residence halls' or 'all full time faculty'. This capability will enable the proper delivery of special broadcasts and targeted communications to communicate to the right person at the right place at the right time and in the right manner. |  | 15 | Medium | Active | Q2 | Marketing & Communication
A | 31 | 794 | 2-Credit Card Processing | Convert CC usage of UGRAD admissions from Touchnet API to UPAY | PCI Compliance Concern - Convert Undergraduate Admissions' acceptance of credit card payments for Admission Deposits and Housing Deposits to UPay from the older TouchNet JSP API which runs in-house on our Orpheus server. UPay is easier to audit for PCI compliance, and is hosted by TouchNet. This UA credit card acceptance application is the last one at LUC using the JSP API. |  | 17 | Small | Active | Q2 | AA-Office of the Provost
A | 58 |  |  | Enterprise Content Management (ECM)/Imaging Implementation | Provides a common method to store, share, process and manage documents in an effective and efficient manner, with ample opportunities to improve student services and build faster, more timely and secure single sources of information for faculty and administrative areas. Also a catalyst for process improvement. |  | 21 | X-Large | Pending | Q4+ | AA-Office of the Provost
A | 59 |  |  | Loyola Alert - Phase II | Determine enhancements to Phase I rollout and if registration will be required. |  | 22 | TBD | Pending | TBD | Facilities
A | 51 | 782 |  | BOT web site | Provide site for Father Garanzini and the Board of Trustees to use for collaboration, such as the sharing of assorted documentation and communications. It should be accessible via LDAP authentication. |  | Not Previously Ranked | Medium | Active | Q1 | Office of the President
A | 47 |  |  | Residential Wireless _ SLLC | Install wireless connectivty to SLLC |  | Not Previously Ranked | Large | Active | Q1 | Academic Affairs
A | 49 | 802 |  | Update to the self-service module of the EMR Point & Click solution and complete the required production reporting for the Wellness Center. | Added efficiencies for student self service and required operational reporting. |  | Not Previously Ranked | Medium | Active | Q1 | Student Affairs
A | 50 |  |  | Relocate Servers from Crown | Complete move of servers from Crown Center data center to new Dumbach data center to make way for new classrooms required in Crown Center space. |  | Not Previously Ranked | Large | Active | Q1 | Information Technology Services
A | 45 |  | 9-Student Experience/Portal | Create UVIDs for incoming Freshmen earlier in the process (Admissions request) This project is tied to the Admitted Students Portal | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. |  | Not Previously Ranked | Large | Active | Q2 | AA-Enrollment Management
A | 46 | 798 | 9-Student Experience/Portal | Admitted Students Portal | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. |  |  | Large | Active | Q2 | AA-Enrollment Management
A | 53 | 463 |  | Import Bio-Demo data into Campus Card to update cardholder records | Import Bio-Demo data into Campus Card to update cardholder records |  | Not Previously Ranked | X-Small | Pending | Q2 | Finance
A | 55 | 743 |  | Integrate the parking permit purchases from the web pages directly into the students account in PS, thereby eliminating the existing manual input of these changes. | Integrate the student parking permit purchases from the web pages directly into the students account in PS, thereby increasing efficiency by eliminating the existing manual input of these changes. Impacts Parking and Bursar's Office processes. |  | Not Previously Ranked | Small | Pending | Q2 | FN-Parking/Business Services

## FY09 Q1-Q2 Plan Of Record
[6 empty] | Plan of Record Data - Key Fields | [5 empty] | Plan of Record Data - New Fields
147
Row Nbr | PSS Nbr | Level | Priority | Program Number | Program Group Name | Project Desc | Major Initiative/Ring Desc | Institutional Impact Statement | Strategic Category | Est. Compl. (QTR) | T-Shirt Sizing | Targeted Start Month (MM/YYYY) | Targeted Finish Month (MM/YYYY) | Status | Health | Primary Customer | Goal Alignment
1 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Ignatius House | Campus Construction Initiatives (22) | Mandated. In support of facilities initiatives. | Infrastructure | Q1 | Large | 2008-01-01 | 2008-07-01 | Active | Green - On Target, No Risk | Facilities
2 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Cudahy Library | Campus Construction Initiatives (22) | Install wireless connectivty to Echo Room | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | Facilities
3 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Crown Center | Campus Construction Initiatives (22) | Remodel CC 114/115 to an Electroinc classroom only | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | Facilities
4 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (22) | Remodeling and moving of staff in Sullivan center | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | Facilities
5 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Bus Shelter | Campus Construction Initiatives (22) | Equip new bus shelter with technology | Infrastructure | Q1 | Small | 2008-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | Facilities
6 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Santa Clara Remodeling | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q1 | Large | 2007-05-01 | 2008-08-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Facilities
7 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (22) | Equip Galvin Auditorium with technology | Infrastructure | Q1 | Small | 2008-04-01 | 2008-08-01 | Active | Green - On Target, No Risk | Facilities
8 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Mertz Hall | Campus Construction Initiatives (22) | Remodel old east west lounge for staff | Infrastructure | Q1 | Small | 2008-05-01 | 2008-08-01 | Active | Green - On Target, No Risk | Facilities
9 |  | R | M | 4 | Construction Projects | Construction Initiatives: - New Dorm's online - Le Moyne, Canisius at LSC | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q1 | Large | 2008-05-01 | 2008-08-08 | Active | Green - On Target, No Risk | Facilities
10 |  | R | M | 4 | Construction Projects | Construction Initiatives: - The Clare - Infrastructure Design and Budgeting | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q2 | Large | 2006-10-01 | 2008-12-01 | Active | Green - On Target, No Risk | Facilities
11 |  | R | M | 4 | Construction Projects | WTC Data Center Remediation | Campus Construction Initiatives (22) | Current data center lacks proper environmental services. This project will address required cooling and power needs. | Infrastructure | Q2 | Large | 2007-10-01 | 2008-12-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
12 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Crown Center Lower level | Campus Construction Initiatives (22) | Upon relocation of servers remodel space for modern languages | Infrastructure | Q4+ | Medium | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
13 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Sullivan Center | Campus Construction Initiatives (22) | CAS to Sullivan | Infrastructure | Q4+ | Small | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
14 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Granada Center | Campus Construction Initiatives (22) | School of Nursing to Granada | Infrastructure | Q4+ | Medium | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | Facilities
15 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Coffey Hall remodeling | Campus Construction Initiatives (22) | Entire building being remodeled | Infrastructure | Q4+ | Large | 2008-04-01 | 2009-07-01 | Active | Green - On Target, No Risk | Facilities
16 |  |  | M | 4 | Construction Projects | Construction Initiatives: - VSTC | Campus Construction Initiatives (22) | Addition on to Gentile for Varsity sports | Infrastructure | Q4+ | Medium | 2008-05-01 | 2009-07-01 | Active | Green - On Target, No Risk | Facilities
17 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Faculty / Staff lounge | Campus Construction Initiatives (22) | New faculty staff lounge adjacent to Cudahy Science | Infrastructure | Q4+ | Medium | 2008-05-01 | 2009-07-01 | Active | Green - On Target, No Risk | Facilities
18 |  |  | M | 4 | Construction Projects | Construction Initiatives: - 20-24 Chicago Ave. | Campus Construction Initiatives (22) | New building on Chicago Avenue attached to 25 E | Infrastructure | Q4+ | Large | 2008-05-01 | 2009-08-01 | Active | Green - On Target, No Risk | Facilities
19 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Mundelein – Infrastructure Design & Implementation Multi - phased. | Campus Construction Initiatives (22) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q4+ | Large | 2007-01-01 | 2009-12-01 | Active | Green - On Target, No Risk | Facilities
20 |  |  | M | 4 | Construction Projects | Construction Initiatives: - 25 E law School Multi phased | Campus Construction Initiatives (22) | Lewis Library and Law School Library are switching locations | Infrastructure | Q4+ | Large | 2008-04-01 | 2010-07-01 | Active | Green - On Target, No Risk | Facilities
21 |  |  | M | 4 | Construction Projects | Construction Initiatives: - Burrowes House for Provost and President | Campus Construction Initiatives (22) | Remodel the old Yellow house. | Infrastructure | Q3 | Medium | TBD | TBD | Pending | Green - On Target, No Risk | Facilities
22 |  | R | M | 4 | Construction Projects | Remodel LT 16 / 17 | Campus Construction Initiatives (22) | Mandated. In support of administration and facilities initiatives. | Infrastructure | Q4+ | Medium |  |  | Hold | Green - On Target, No Risk | Facilities
23 |  |  | M | 5 | Security Projects | PCI/DSS Compliance | Security Initiatives (PIRG & Audit Related) | Compliance to the PCI/DSS standard is mandatory. Failure to comply with the standard can result in significant fines and a critical risk from a PR perspective. Additionally, if a breach of credit card data occurs while Loyola is non-compliant, Loyola would be forced to comply as a Level 1 merchant in addition to a multitude of additional fines. Total costs for such noncompliance or a breach could be significant. | Continuous Service Development | Q4 | X-Large | 2008-03-01 | 2009-06-01 | Active | Orange - Slightly Off Target, Several Risks or Unknowns | Finance | 9: Promote a culture of service excellence at all levels.
24 |  |  | M |  |  | Create Electronic space in Echo Room of Cudahy Library | Cudahy Library Echo Room Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs
25 |  |  | M |  |  | Security Initiative | Safety for on campus | Implement a Wide area emergency broadcast system via an announcement to emergency phones strategically locate4d on campus | Student Technology Support | Q1 | Small | 2008-04-01 | 2008-08-01 | Active | Green - On Target, No Risk | Facilities
26 |  |  | M |  |  | Add Display to IC Reading Room | Information Commons Reading Room Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-06-01 | 2008-09-01 | Active | Green - On Target, No Risk | Academic Affairs
27 |  |  | M |  |  | Provide Technology in LUMA @ WTC | LUMA Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-04-01 | 2008-09-01 | Active | Green - On Target, No Risk | Academic Affairs
28 |  |  | M |  |  | Create Electronic space on 4th Floor of Information Commons | Information Commons 4th Floor Technology | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q2 | Medium | 2008-06-01 | 2008-12-01 | Active | Green - On Target, No Risk | Academic Affairs
29 | 739 | R | A | 1 | Student System Upgrade | Upgrade RDS to PeopleSoft 9.0 Tables The RDS will be upgraded to extract data from PeopleSoft 9.0. | Student System Upgrade | Maintain functionality of the student reporting database (RDS) after LOCUS upgrade until a more permanent solution is implemented. | Academic & Faculty Support | Q1 | Medium | 2007-10-31 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
30 | 667 | R | A | 1 | Student System Upgrade | LOCUS Campus Solutions 9.0 upgrade | Student System Upgrade | Continuation of support and regulatory updates for LOCUS after current support ends on 8/31/2007. Required step of the SIS upgrade. | Academic & Faculty Support | Q1 | X-Large | 2007-05-01 | 2008-07-01 | Active | Green - On Target, No Risk | AA-Office of the Provost | 3: Enhance the quality of campus life for resident and commuter students.
31 | 794 |  | A | 2 | Credit Card Processing | Convert CC usage of UGRAD admissions from Touchnet API to UPAY |  | PCI Compliance Concern - Convert Undergraduate Admissions' acceptance of credit card payments for Admission Deposits and Housing Deposits to UPay from the older TouchNet JSP API which runs in-house on our Orpheus server. UPay is easier to audit for PCI compliance, and is hosted by TouchNet. This UA credit card acceptance application is the last one at LUC using the JSP API. | Administrative Initiatives | Q2 | Small | 2008-05-01 | 2008-12-01 | Active | Green - On Target, No Risk | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
32 | 320 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Self Service Apply for Graduation | LOCUS Enhancements (16) | Unify disparate school graduation applications to support self service for students applying for graduation. | Academic & Faculty Support | Q1 | Small | 2007-04-01 | 2008-09-01 | Hold |  | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
33 | 640 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: Requested Rooms report over time by department | LOCUS Enhancements (16) | Provides the ability to review trends in academic space utilization. | Administrative Initiatives | Q1 | Small | 2007-06-01 | 2008-09-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
34 | 319 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Grade Change process | LOCUS Enhancements (16) | Automate grade change process for routine grade changes submitted by faculty. | Academic & Faculty Support | Q1 | Medium | 2007-05-07 | 2008-09-01 | Hold |  | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
35 | 632 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: Correcting unpaid balance on Self-Service Make A Payment page. | LOCUS Enhancements (16) | Clarify balance due related to unapplied credits. | Student Technology Support | Q1 | Medium | 2007-07-01 | 2008-09-01 | Active | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
36 | 641 | R | A | 3 | LOCUS Enhancements | Load Previous Education to LOCUS from Grad R-Plus | LOCUS Enhancements (16) | Enhance preparation of commencement program & enhance student record completeness. | Academic & Faculty Support | Q2 | Large | 2007-06-01 | 2008-11-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
37 | 727 | R | A | 3 | LOCUS Enhancements | A report that shows the results of each night's Tuition Calculation results. | LOCUS Enhancements (16) | Report used to identify students that are charged incorrectly, will eliminate student complaints | Academic & Faculty Support | Q2 | Small | 2007-11-13 | 2008-12-01 | Active | Green - On Target, No Risk | General Accounting | 9: Promote a culture of service excellence at all levels.
38 | 439 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: - Load AP/MDT test results to LOCUS, post to student records, in an automated (timely) fashion to assist Admissions Advisement. | LOCUS Enhancements (16) | Automate currently manual processes of acquiring external placement/credit test results from authorized testing vendors. | Academic & Faculty Support | Q2 | Small | 2007-10-01 | 2008-12-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | AA-Enrollment Management | 5: Improve the academic quality of incoming students and academic programs.
39 | 568 | R | A | 3 | LOCUS Enhancements | Debug Account Audit Statement | LOCUS Enhancements (16) | Improve useability of Account Audit Statement report. | Administrative Initiatives | Q2 | Large |  | 2008-12-01 | Active | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
40 |  | R | A | 5 | Security Projects | Personal Information Risk Group (PIRG) Policy Implementation | Security Initiatives (PIRG & Audit Related) | Create and implement the required policies, supporting procedures and training to protect and govern personally identifiable information (PII). The policies and processes are required to enable institutional governance. Not implementing will result in an increased risk to the unwanted exposure of PII. | Continuous Service Development | Q2 | Large | 2006-09-01 | 2008-10-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Office of the President | 9: Promote a culture of service excellence at all levels.
41 |  | R | A | 5 | Security Projects | Personal Information Risk Group (PIRG) Disk Encryption Rollout | Security Initiatives (PIRG & Audit Related) | Identify and implement the necessary software, supporting procedures and training to identify and encrypt personally identifiable information (PII). Not implementing the software and corresponding procedures will result in an increased risk to the unwanted exposure of PII. | Continuous Service Development | Q2 | Large | 2007-11-01 | 2008-11-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Office of the President | 9: Promote a culture of service excellence at all levels.
42 | 423 | R | A | 5 | Security Projects | Blackboard Campus Card - switch from Social Security Number to LID as the primary key within the Blackboard database. | Eliminate SSN's from Campus Card | Reduce security risks with Personal Information by removing SSN from the Campus Card system. | Administrative Initiatives | Q2 | Medium | 2007-08-01 | 2008-11-01 | Active | Green - On Target, No Risk | FN-Campus Card | 9: Promote a culture of service excellence at all levels.
43 | 635 | R | A | 8 | Advancement | Upgrade Advancement databases to 10g | BSR/Smartcall Upgrade | Required first step to upgrade the Advancement application (see PSS 325,339). Additionally, the upgrade of the database to 10g provides more robust database tools fr performance tuning and maintenance. | Administrative Initiatives | Q2 | Medium | 2008-02-01 | 2008-10-01 | Active | Green - On Target, No Risk | Advancement | 10: Enhance its development efforts and alumni engagement.
44 | 325, 339 | R | A | 8 | Advancement | Upgrade BSR/SmartCall to new release | BSR/Smartcall Upgrade | New functions allow gathering more specific information on donors so as to better target fund raising efforts. Security of the application is greatly enhanced. Additional functionality in the areas of Cell Phone Management, Allocation Tracking, Gift Processing, Email address consolidation and provides the ability to have release note access | Administrative Initiatives | Q2 | Large | 2007-05-01 | 2008-10-01 | Active | Green - On Target, No Risk | Advancement | 10: Enhance its development efforts and alumni engagement.
45 |  |  | A | 9 | Student Experience/Portal | create UVIDs for incoming Freshmen earlier in the process (Admissions request) This project is tied to the Admitted Students Portal |  | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. | Student Technology Support | Q2 | Large | 2008-01-01 | 2008-11-01 | Active | Green - On Target, No Risk | AA-Enrollment Management | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
46 | 798 | R | A | 9 | Student Experience/Portal | Admitted Students Portal |  | Create a website/portal exclusively for newly admitted students to provide custom information in an easily accessible and “exclusive” site, offering a more personalized and community-based online experience to admitted students. We believe this more contemporary content delivery method will engage admitted students with Loyola earlier and allow them to make connections with other students with similar interests during the admissions process. | Student Technology Support | Q2 | Large | 2008-05-01 | 2008-11-01 | Active | Green - On Target, No Risk | AA-Enrollment Management | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
47 |  |  | A |  |  | Residential Wireless _ SLLC | Wireless Expansion | Install wireless connectivty to SLLC | Infrastructure | Q1 | Large | 2008-05-01 | 2008-08-01 | Active | Green - On Target, No Risk | Academic Affairs
48 | 32 | R | A | 3 | LOCUS Enhancements | Implement collections module within the student system | LOCUS Enhancements (16) | Currently the Busar staff use excel list from the Collectors report.Any updates to a student account are done manually. Utilization of the Collectors Module should streamline the process, improve workflow and communication with staff.Bottom line impact should be a reduced accounts receivables and fewer acctounts turned over to collection agencys | Administrative Initiatives | Q1 | Small |  | 2008-08-01 | Active | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
49 | 802 | R | A |  |  | Update to the self-service module of the EMR Point & Click solution and complete the required production reporting for the Wellness Center. | Wellness Electronic Medical Records | Added efficiencies for student self service and required operational reporting. | Student Technology Support | Q1 | Medium | 2007-11-01 | 2008-08-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
50 |  |  | A |  |  | Relocate Servers from Crown |  | Complete move of servers from Crown Center data center to new Dumbach data center to make way for new classrooms required in Crown Center space. | Infrastructure | Q1 | Large |  | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services
51 | 782 | R | A |  |  | BOT web site |  | Provide site for Father Garanzini and the Board of Trustees to use for collaboration, such as the sharing of assorted documentation and communications. It should be accessible via LDAP authentication. | Administrative Initiatives | Q1 | Medium | 2008-04-01 | 2008-09-01 | Active | Green - On Target, No Risk | Office of the President | 9: Promote a culture of service excellence at all levels.
52 | 762 | R | A |  |  | Messaging and Information Lists | Messaging and Information Lists | There is a need to be able to easily create email lists for targeted groups such as faculty, staff or students taking into consideration each individuals status and then sending the email. Consideration must be given to the abiliy to break these groups down into smaller targeted groups such as: 'all currently enrolled students in the business school that live in the residence halls' or 'all full time faculty'. This capability will enable the proper delivery of special broadcasts and targeted communications to communicate to the right person at the right place at the right time and in the right manner. | Continuous Service Development | Q2 | Medium | 2008-01-01 | 2008-10-01 | Active | Green - On Target, No Risk | Marketing & Communication | 9: Promote a culture of service excellence at all levels.
53 | 463 |  | A |  |  | Import Bio-Demo data into Campus Card to update cardholder records |  | Import Bio-Demo data into Campus Card to update cardholder records | Administrative Initiatives | Q2 | X-Small | 2008-09-01 | 2008-10-01 | Pending | Green - On Target, No Risk | Finance | 9: Promote a culture of service excellence at all levels.
54 | 709 | R | A |  |  | This is the next phase of IDM3. The immediate need is to provide SSOM University employees the ability to authenticate to University resources to administer their own benefits. The secondary need is to uniquely identify all Loyola employees (Hospital and University) so that we might identify and use the same UVID on either side of Loyola. The SST stands for Shared Source of Truth. | LDAP Authentication w/ LUMC | Provide a share database that will allow LUMC and LUC to verify uvid, reducing redundancy and conflicts. Provides a method to streamline access to shared resources. | Administrative Initiatives | Q2 | Large | 2007-06-01 | 2008-12-01 | Active | Green - On Target, No Risk | Human Resources | 8: Strengthen it relationship with the City of Chicago and the neighborhoods of the Water Tower, Lake Shore and Medical Center Campuses.
55 | 743 |  | A |  |  | Integrate the parking permit purchases from the web pages directly into the students account in PS, thereby eliminating the existing manual input of these changes. |  | Integrate the student parking permit purchases from the web pages directly into the students account in PS, thereby increasing efficiency by eliminating the existing manual input of these changes. Impacts Parking and Bursar's Office processes. | Administrative Initiatives | Q2 | Small |  | 2008-12-01 | Pending |  | FN-Parking/Business Services | 9: Promote a culture of service excellence at all levels.
56 | 799 | R | A | 3 | LOCUS Enhancements | Update IPEDS Reporting | LOCUS Enhancements (16) | Changes are needed to support the new IPEDS requirements. IPEDS now requires universities to report further detail on race and ethnicity. Data collection points such as applications will need to be altered as well as R+ appion and interface, SIS and associated reports. | Student Technology Support | Q2 | Large | 2008-08-01 | 2008-12-01 | Pending |  | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
57 | 735 | R | A |  |  | This project will investigate, select, and implement an upgrade from our current Unix based Blackboard Transaction System to a system based on the windows operating system and a supported database. From the SSR: "Upgrade the existing Campus Card transaction system to a windows-based system. This upgrade will provide a more user-friendly application and provide many potential savings... | Campus Card Platform Upgrade | Enhance Campus Card functionality including: - improved process for issuing cards - point of sale transaction flow - interfaces with other systems such as RMS meal plans and MAXXESS security - improved reporting; and - easier maintenance. | Infrastructure | Q4 | Large | 2007-10-01 | 2009-05-01 | Active | Green - On Target, No Risk | Finance | 3: Enhance the quality of campus life for resident and commuter students.
58 |  | R | A |  |  | Enterprise Content Management (ECM)/Imaging Implementation | Enterprise Imaging Implementation (ECM) | Provides a common method to store, share, process and manage documents in an effective and efficient manner, with ample opportunities to improve student services and build faster, more timely and secure single sources of information for faculty and administrative areas. Also a catalyst for process improvement. | Administrative Initiatives | Q4+ | X-Large | 2008-07-01 | 2009-06-01 | Pending | Green - On Target, No Risk | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
59 |  | R | A |  |  | Loyola Alert - Phase II | BCDR & Emergency Notification Projects | Determine enhancements to Phase I rollout and if registration will be required. | Infrastructure | TBD | TBD | TBD | TBD | Pending |  | Facilities | 3: Enhance the quality of campus life for resident and commuter students.
60 | 690 |  | B | 2 | Credit Card Processing | Credit Card Processing, Preschool Tuition Payment | Credit Card Processing |  | Administrative Initiatives | Q2 | Small |  | 2008-12-01 | Pending |  | Finance | 9: Promote a culture of service excellence at all levels.
61 | 752 |  | B | 2 | Credit Card Processing | Credit Card Processing, Executive Education | Credit Card Processing |  | Administrative Initiatives | Q4 | Small | 2008-02-01 | 2009-06-01 | Pending |  | Finance | 9: Promote a culture of service excellence at all levels.
62 | 196 | R | B | 3 | LOCUS Enhancements | Enhancement to Locus - Federal Work Study project | LOCUS Enhancements (16) | Improve monitoring of FWS awards by automating Lawson payroll data to LOCUS. | Academic & Faculty Support | Q1 | Medium | 2006-07-01 | 2008-09-01 | Hold |  | Academic Affairs | 9: Promote a culture of service excellence at all levels.
63 | 714 | R | B | 3 | LOCUS Enhancements | When a staff member enters direct deposit information for a student, they can use effective dated rows and an inactive/active status flag to track the history of a student's direct deposit account changes. But shen students manage their own direct deposit information via self-service, there is no effective dating - they overwrite their previous information. | LOCUS Enhancements (16) |  | Administrative Initiatives | Q2 | Large |  | 2008-11-01 | Pending |  | Office Of The Bursar | 9: Promote a culture of service excellence at all levels.
64 | 479 | R | B | 3 | LOCUS Enhancements | LOCUS Enhancements: - Review Graduate Repeat Rules, GPA Calc CS 9.0 may negate this request | LOCUS Enhancements (16) |  | Academic & Faculty Support | Q2 | Small |  | 2008-12-01 | Pending |  | AA-Registration & Records | 5: Improve the academic quality of incoming students and academic programs.
65 |  |  | B | 5 | Security Projects | Security Audit - Response to Open Items - FY08 |  | Remediation of the high and medium risk items identified in the annual ITS security audit is required. Not implementing the recommendations will result in an increased risk to the overall information security of the institution. | Infrastructure | Q2 | Medium | 2007-08-01 | 2008-12-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Office of the President
66 |  |  | B | 5 | Security Projects | Annual Information Security Assessment - FY09 | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q3 | Medium | 2008-10-01 | 2009-03-01 | Pending | Green - On Target, No Risk | Information Technology Services
67 | 734 |  | B | 5 | Security Projects | Secure all Oracle bkup directories on all Oracle servers. |  | Secure databases from internal and external attacks | Infrastructure | Q4 | Small |  | 2009-06-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
68 |  |  | B | 5 | Security Projects | Information Security Monitoring Program (IPS, vulenrability, app/pen testing) | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q4 | Medium | 2008-11-01 | 2009-06-01 | Pending | Green - On Target, No Risk
69 |  |  | B | 5 | Security Projects | Information Security Awareness | Security Initiatives (PIRG & Audit Related) |  | Continuous Service Development | Q4 | Small | 2008-08-01 | 2009-06-01 | Pending | Green - On Target, No Risk
70 | 624 | R | B | 6 | “Housing/ Scheduling” Projects | Rollout of the RMS Student Web Functionality | RMS Housing Application Improvements | provide online real-time shopping for available rooms, meal plans and communication of assignment status | Student Technology Support | Q4 | Large | 2007-10-01 | 2009-06-01 | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
71 |  |  | B |  |  | Upgrade Technology in Provost's Office @ WTC | Provost's Office Conference Room Upgrade | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | X-Small | 2008-06-01 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs
72 |  |  | B |  |  | Develop, deploy and evaluate two pilots for online teacher course evaluation processes using commercial products | Develop, deploy and evaluate pilots for online teacher course evaluation processes |  | Academic & Faculty Support | Q1 | Medium | 2007-11-01 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs
73 |  | R | B |  |  | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) |  | Continuous Service Development | Q1 | Medium | 2008-01-01 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
74 |  |  | B |  |  | Upgrade Technology in Simpsom MPR | Simpsom MPR Refresh | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms, conference rooms, and other spaces defined in construction projects. | Continuous Service Development | Q1 | Small | 2008-06-01 | 2008-07-01 | Active | Green - On Target, No Risk | Academic Affairs
75 |  |  | B |  |  | Upgrade Group Study & Equipment Reservation System(s) | Upgrade Group Study & Equipment Reservation System(s) |  | Administrative Initiatives | Q1 | Small | 2008-06-01 | 2008-08-01 | Active | Green - On Target, No Risk | Information Technology Services | 6: Promote multidisciplinary collaborations.
76 |  |  | B |  |  | Expand Equipment Loan Program with additional online training and equipment available through AT&T Grant | Expansion of Digital Media Equipment Loan Program |  | Continuous Service Development | Q1 | Medium | 2008-06-01 | 2008-08-01 | Active | Green - On Target, No Risk | AA-Colleges & Schools | 7: Expand its investment in research and scholarship in order to take full advantage of its academic strengths.
77 |  | R | B |  |  | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) | Pilot Rich Media Offerings (Podcasting, Blog/Wiki, Video Streaming) |  | Continuous Service Development | Q4+ | Large | 2008-01-01 | 2008-08-01 | Active | Green - On Target, No Risk | Academic Affairs
78 |  |  | B |  |  | Network Initiative - Damen Hall | Network Enhacement | upgrade the network infrastructure in the closets | Infrastructure | Q1 | Small | 2008-04-01 | 2008-08-01 | Active | Green - On Target, No Risk | Information Technology Services
79 |  |  | B |  |  | Phase II of Call Tracking System Implementation | Call Tracking Self Service |  | Continuous Service Development | Q1 | Medium | 2008-01-01 | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
80 |  | R | B |  |  | Add technology “dashboard” metrics to ITS website for all of ITS | Develop ITS Services Direction & Metrics |  | Continuous Service Development | Q1 | Medium | 2008-06-01 | 2008-09-01 | Active | Green - On Target, No Risk | Academic Affairs | 9: Promote a culture of service excellence at all levels.
81 | 657 |  | B |  |  | Tuition Benefit automation |  |  | Student Technology Support | Q1 | Large |  | 2008-09-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Human Resources | 9: Promote a culture of service excellence at all levels.
82 | 736 |  | B |  |  | Mismatch SSN between Lawson and PS--Create Reports and views that can help HR(Carol McCormack) and Student Admin (Kris Dagget) resolve SSN discrepancies between LOCUS and Lawson. |  | Mismatch SSN between Lawson and PS- Create Reports and views that will coordinate the resolving issues between HR and PS | Administrative Initiatives | Q1 | Small |  | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
83 |  |  | B |  |  | Develop support model proposal and update budget plan for current technology in the Information Commons | Enhance Information Commons Service Offerring |  | Continuous Service Development | Q1 | Small | 2008-05-01 | 2008-09-01 | Active | Green - On Target, No Risk | Academic Affairs
84 |  | R | B |  |  | Academic Wireless - Flanner & LSB | Wireless Expansion | Expansion of wireless. Strengthens Loyola's competitiveness | Student Technology Support | Q1 | Large | 2008-01-01 | 2008-09-08 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
85 |  |  | B |  |  | Build plan and timeline proposal for In-sourced Blackboard learning System | Build plan and timeline proposal for In-sourced Blackboard learning System |  | Academic & Faculty Support | Q2 | Large | 2008-04-01 | 2008-10-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
86 | 588 |  | B |  |  | Entrance control for Gentile Center |  | This project has changed from building a small cabability to a purchase of a hosted ticket application that handles season ticket holders and students | Administrative Initiatives | Q2 | Small |  | 2008-10-01 | Active | Green - On Target, No Risk | Student Affairs | 9: Promote a culture of service excellence at all levels.
87 |  |  | B |  |  | Define requirements and determine feasibility for setting up learning object repository | Develop requirements w/ Academic Affairs |  | Academic & Faculty Support | Q2 | Medium | 2008-06-01 | 2008-10-01 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
88 |  |  | B |  |  | Transition from "Call Track" system to HEAT for ResNet support application | ResNet System Replacement |  | Continuous Service Development | Q2 | Medium | 2008-04-01 | 2008-10-01 | Active | Green - On Target, No Risk | Academic Affairs
89 |  |  | B |  |  | Deploy Teamspot Application at Water Tower Campus | Teamspot Deployment |  | Continuous Service Development | Q2 | Small | 2008-04-01 | 2008-10-01 | Active | Green - On Target, No Risk | Academic Affairs
90 |  |  | B |  |  | iHeat - provides access to Heat call logging(including First level support) | Provides access to Heat Call logging |  | Continuous Service Development | Q2 | Medium | 2008-06-01 | 2008-11-01 | Active | Green - On Target, No Risk | Academic Affairs | 9: Promote a culture of service excellence at all levels.
91 |  |  | B |  |  | Heat Knowledge Base | Knowledge Base activation |  | Continuous Service Development | Q2 | Medium | 2008-06-01 | 2008-11-01 | Active | Green - On Target, No Risk | Academic Affairs | 9: Promote a culture of service excellence at all levels.
92 |  |  | B |  |  | Implementation of Storage Expansion - Faculty / Staff | Faculty/Staff Storage Expansion |  | Academic & Faculty Support | Q2 | Large | 2008-06-08 | 2008-12-01 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
93 |  |  | B |  |  | Zen Configuration Management. This will require a rebuild of every application we currently use. | Zen Configuration Management | Improve Application deployment and asset management. | Continuous Service Development | Q2 | Large |  | 2008-12-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
94 | 700 |  | B |  |  | Enhancements to the Rambler Bucks charge authorization system. Currently, requests are collected on the web form and then entered manually in PeopleSoft and Blackboard. The new functionality requested would provided automated processes. Primary request is to post amount of Rambler Bucks requested by student to their account in PeopleSoft. Secondary request is to load Rambler Bucks amount into the Blackboard Transaction system. Requested delivery date - December 15, 2007 |  | Reduce the need for manual intervention in posting amounts to the students account in PeopleSoft and Blackboard | Administrative Initiatives | Q2 | Small |  | 2008-12-01 | Pending |  | Finance | 9: Promote a culture of service excellence at all levels.
95 | 742 |  | B |  |  | Modify the Convio to BSR interface to accomodate the addition of gifts being made through the Convio web site. |  | Modify the Convio to BSR interface to accomodate the addition of gifts being made through the Convio web site. | Administrative Initiatives | Q2 | Medium |  | 2008-12-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Advancement | 10: Enhance its development efforts and alumni engagement.
96 |  |  | B |  |  | iHeat - provides access to Heat call logging(including First level support) | Provides access to Heat Call logging |  | Continuous Service Development | Q2+ | Medium | 2008-08-01 | 2008-12-01 | Pending | Green - On Target, No Risk | Academic Affairs
97 |  |  | B |  |  | Develop and Propose ITS Certification Model | Develop and Propose ITS Certification Model |  | Administrative Initiatives | Q2 | Medium | 2008-06-01 | 2008-12-01 | Active | Green - On Target, No Risk | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
98 |  | R | B |  |  | Patching Policies and Metrics for OS Patch Management | Develop ITS Services Direction & Metrics | Improve on what is today a manual process. | Continuous Service Development | Q2 | Medium | 2007-11-01 | 2008-12-08 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
99 |  | R | B |  |  | Implement Crestron RoomView - Remote Management Software | Remote Electronic Classroom Management |  | Academic & Faculty Support | Q3 | Small | 2008-06-01 | 2009-01-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
100 |  |  | B |  |  | Develop, deploy and evaluate pilot for making online assessment through Blackboard more secure for high stakes testing, e.g., Respondus | Develop and deploy pilot for making online assessment through Blackboard more secure |  | Academic & Faculty Support | Q3 | Medium | 2008-09-01 | 2009-01-01 | Pending | Green - On Target, No Risk | Academic Affairs
101 |  |  | B |  |  | Deliver Blackboard and other Technology Workshops w/Academic Affairs | Deliver Blackboard and other Technology Workshops w/Academic Affairs |  | Academic & Faculty Support | Q4 | Medium | 2008-05-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs
102 |  |  | B |  |  | Working with Academic Affairs, develop and implement support paradigm for Web 2.0 tools in teaching and learning, e.g., podcasting in Blackboard (covers training) | Working with Academic Affairs, develop and implement support paradigm for Web 2.0 tools in teaching and learning, e.g., podcasting in Blackboard (covers training) |  | Academic & Faculty Support | Q4 | Large | 2008-05-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs
103 |  |  | B |  |  | Enhanced training initiatives and documentation to expand modes of delivery, e.g., narrated tutorials and use of Web 2.0 tools, e.g., blogs and wikis | Enhanced training initiatives and documentation to expand modes of delivery, e.g., narrated tutorials and use of Web 2.0 tools, e.g., blogs and wikis |  | Academic & Faculty Support | Q4 | Large | 2008-01-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs
104 |  |  | B |  |  | Working with Academic Affairs and Web Development, design and implement web "portal" to teaching and learning technologies | Working with Academic Affairs and Web Development, design and implement web "portal" to teaching and learning technologies |  | Academic & Faculty Support | Q4 | Large | 2008-06-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs
105 |  |  | B |  |  | Develop and Implement Summer Training Camps for Area High School Students | Offer Summer Training Camps and Clinics for Area Advanced High School Students |  | Academic & Faculty Support | Q4+ | Medium | 2008-06-01 | 2009-04-01 | Active | Green - On Target, No Risk | Academic Affairs | 8: Strengthen it relationship with the City of Chicago and the neighborhoods of the Water Tower, Lake Shore and Medical Center Campuses.
106 |  | R | B |  |  | Develop long-term strategy for LMS | LMS Strategic Planning |  | Academic & Faculty Support | Q4+ | X-Large | 2007-07-01 | 2009-05-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
107 |  |  | B |  |  | Develop requirements w/ Academic Affairs for Piloting Sakai | Develop requirements w/ Academic Affairs for Piloting Sakai |  | Academic & Faculty Support | Q4+ | X-Large | 2008-08-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs | 3: Enhance the quality of campus life for resident and commuter students.
108 |  |  | B |  |  | Position support for Blackboard, Opinio, Research Support Systems, and Listserv Managemet for Self-Service Call Center | Position support for Blackboard, Opinio, Research Support Systems, and Listserv Managemet for Self-Service Call Center |  | Continuous Service Development | Q4 | Medium | 2008-06-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
109 |  |  | B |  |  | Connectivity to the Wellness Center |  | Provide more reliable service for wellness Center application. Requires City ROW | Infrastructure | Q1 | Large | 2008-07-01 | 2009-07-01 | Active | Green - On Target, No Risk | Student Affairs | 3: Enhance the quality of campus life for resident and commuter students.
110 |  |  | B |  |  | Network Initiative - LSC | network enhacement | Roll out VOIP | Infrastructure | Q4+ | Small | 2008-05-01 | 2009-07-01 | Active | Green - On Target, No Risk | Information Technology Services
111 |  |  | B |  |  | Determine subsequent Phases of IDM3 with SIC group : Library; Maxxess; Halas (employees); Parking; Locus login | LDAP Authentication w/ LUMC |  | Continuous Service Development |  | TBD |  | 2009-12-01 | Hold |  | Human Resources | 9: Promote a culture of service excellence at all levels.
112 |  |  | B |  |  | Cost Containment & Reduction - Implement local and long distance contracts - Combine DS1 Services into a coterminous agreement - Evaluate Desktop Support contract | Cost Containment & Reduction | Overall cost savings to the University | Administrative Initiatives | Q4 | Small | 2007-07-01 | On-going | Active | Yellow - Target in Jeopardy, Risks Being Managed, Unknowns Exist | Information Technology Services | 9: Promote a culture of service excellence at all levels.
113 |  |  | B |  |  | New Technology Testing (Vista, Office 2007, Share Point) | New Technology Testing (Vista, Office 2007, Share Point) | Determine how these technologies will fit in our environment. Plans to deploy Office 2007 in labs Fall08 | Continuous Service Development | Q2 | Medium | 2008-06-07 | On-going | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
114 |  |  | B |  |  | Offer Digital Media Courses for Students, Faculty and Staff on a Variety of Topics, including: Video Production, Animation, Newspaper Construction, Website Design, Web 2.0, Scripting, etc. | Offer Digital Media Clinics & Seminars |  | Academic & Faculty Support | Q4+ | Medium | 2008-08-01 | On-going | Pending | Green - On Target, No Risk | AA-Colleges & Schools | 7: Expand its investment in research and scholarship in order to take full advantage of its academic strengths.
115 | 663 | R | B |  |  | Enhancements to Commuter Student Parking Application | Commuter Student Parking Enhancements | Administrative enhancements to help automate processes including web focus reporting. Project on hold pending requirements detail gathering. | Administrative Initiatives | Q4 | Small | 2007-11-01 | TBD | Hold |  | Student Affairs | 9: Promote a culture of service excellence at all levels.
116 |  |  | B |  |  | Rome Center Support (desktop, network, services, Skype) | Rome Center Technology Review | To assist in creating processes that will improve the delivery of services to students attending classes at JFRC. Also to begin laying the foundation for infrastructure requirements to support the new campus. | Continuous Service Development | Q3 | Medium | 2007-06-01 | TBD | Active | Green - On Target, No Risk | Academic Affairs | 4: Strengthen the international dimensions of its programs and outreach.
117 | 719 |  | B |  |  | This is a request to enhance the functionality within PSS. It is desired to have the capability to identify relationships between related projects ie a Parent-Child relationship. This will allow the grouping of these projects. As an example we have several projects that are being implemented via the TouchNet Marketplace tool. We are tracking each project separately but have a need to group the |  |  | Continuous Service Development | Q2 | Small |  | TBD | Pending |  | Information Technology Services | 9: Promote a culture of service excellence at all levels.
118 | 800 |  | B |  |  | BI - DW Stragety creation |  | Business Intelligence and Data Warehouse stragety definition needs to be completed in order to determine the future direction of our student reporting. The RDS needs to be replaced with a student data warehouse to help facilitate institutional reporting on current as well as historical reporting. Consideration needs to be given in the design for implementing a student centric warehouse with the ability to expand to an enterprise data warehouse as needed. | Administrative Initiatives | Q2 | Large | 2008-08-01 | TBD | Pending |  |  | 5: Improve the academic quality of incoming students and academic programs.
119 | 754 |  | C | 2 | Credit Card Processing | Credit Card Processing for Gift Shop for LUMA |  |  | Administrative Initiatives | Q2 | Small | 2008-03-01 | 2008-12-01 | Pending |  | Finance | 9: Promote a culture of service excellence at all levels.
120 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Bioethics | Credit Card Processing |  | Administrative Initiatives |  | TBD |  |  | Hold |  | Finance | 9: Promote a culture of service excellence at all levels.
121 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Continuing Medical Education | Credit Card Processing |  | Administrative Initiatives |  | TBD |  |  | Hold |  | Finance | 9: Promote a culture of service excellence at all levels.
122 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Social Work | Credit Card Processing |  | Administrative Initiatives |  | TBD |  |  | Hold |  | Finance | 9: Promote a culture of service excellence at all levels.
123 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, SSOM Ministry | Credit Card Processing |  | Administrative Initiatives |  | TBD |  |  | Hold |  | Finance | 9: Promote a culture of service excellence at all levels.
124 |  |  | C | 2 | Credit Card Processing | Credit Card Processing, Theology | Credit Card Processing |  | Administrative Initiatives |  | TBD |  |  | Hold |  | Finance | 9: Promote a culture of service excellence at all levels.
125 | 713 | R | C | 3 | LOCUS Enhancements | Currently, the reason code field does not have to be populated in order to generate a charge reversal or payment reversal. However, that creates a reporting issue. We should know why a payment or a charge was reversed. So, the reason code should be a required field on the Charge Reversal and Payment Reversal pages. | LOCUS Enhancements (16) |  | Administrative Initiatives | Q2 | Medium |  | 2008-12-01 | Active | Green - On Target, No Risk | Office Of The Bursar | 9: Promote a culture of service excellence at all levels.
126 | 712 | R | C | 3 | LOCUS Enhancements | When creating departmental receipts, currently users must manually key in the LUCHI business unit into this field. For faster data entry, it would be convenient if the business unit defaulted in this field when the page is loaded. | LOCUS Enhancements (16) |  | Administrative Initiatives | Q2 | Small |  | 2008-12-01 | Hold |  | Office Of The Bursar | 9: Promote a culture of service excellence at all levels.
127 | 433 | R | C | 3 | LOCUS Enhancements | LOCUS Enhancements: - Change the transcript level default on the entry of transfer credit to "Official". The current default is "Unofficial" and does not print the summary on the official transcript. | LOCUS Enhancements (16) |  | Academic & Faculty Support | Q2 | Small | 2006-07-01 | 2008-12-01 | Active | Green - On Target, No Risk | AA-Registration & Records | 5: Improve the academic quality of incoming students and academic programs.
128 | 756 | R | C | 7 | BCDR/Failover | Install DataGuard on Advancement databases | BCDR & Emergency Notification Projects | Provide a failover system to prevent database outage when production database fail | Infrastructure | Q2 | Small | 2007-10-01 | 2008-12-01 | Active | Green - On Target, No Risk | Advancement | 9: Promote a culture of service excellence at all levels.
129 | 757 | R | C | 7 | BCDR/Failover | Install DataGuard on LUC Databases (in house developed, R25, CMS, Opinio, etc.) | BCDR & Emergency Notification Projects | Provide a failover system to prevent database outage when production database fail | Infrastructure | Q2 | Small | 2007-10-01 | 2008-12-01 | Pending |  | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
130 | 803 |  | C | 9 | Student Experience/Portal | Enhance the look and feel of the LOCUS portal. |  | Project intended to support goal of increasing retention and enhanced service to current students. Objective is to improve sudent access to the information they need in an efficient, convenient and appealing way. It is intended that students will transistion from the "Admitted Students" portal thie current students portal. | Student Technology Support | TBD | TBD | TBD | TBD | Pending |  | AA-Office of the Provost
131 |  |  | C |  |  | Improve Spam Detection | Reduction in SPAM | We currently have a spam detection system in place. This project is to enhance the current system by installing appliances to further reduce SPAM. | Continuous Service Development | Q1 | Large |  | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services
132 | 258 |  | C |  |  | Enhancements to Project Status System | Enhancements to Project Status System |  | Administrative Initiatives | Q1 | Large | 2007-01-01 | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
133 |  |  | C |  |  | Leopard OS Testing |  | Continue to integrate Mac platforms into our environment | Infrastructure | Q1 | Medium | 2008-01-08 | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services
134 |  |  | C |  |  | Phased Implementations: - Quality Assurance Methodology, pilot projects and begin training | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q1 | Small | 2008-01-01 | 2008-09-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
135 |  |  | C |  |  | Phased Implementations: - Enterprise Architecture Principles & Framework | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q2 | Medium | 2007-03-01 | 2008-10-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Information Technology Services | 9: Promote a culture of service excellence at all levels.
136 |  |  | C |  |  | Phased Implementations: - Gate Review Formalization | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q2 | Small | 2007-01-01 | 2008-12-01 | Hold | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Information Technology Services | 9: Promote a culture of service excellence at all levels.
137 |  |  | C |  |  | Recommendation for Storage Expansion - Students | Recommendation for Storage Expansion - Students |  | Student Technology Support | Q2 | Small |  | 2008-12-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
138 |  |  | C |  |  | Boston College Web Presence at LUC | AJCU Collaboration | No impact on users at LUC. This has impact only on Boston College. | Continuous Service Development | Q2 | Small |  | 2008-12-01 | Active | Green - On Target, No Risk | Information Technology Services | 9: Promote a culture of service excellence at all levels.
139 | 732 |  | C |  |  | Update the current software request form http://orpheus.it.luc.edu/infotech/icomp/swreq.cfm with a new form. The old one is very outdated; additional and different information now needs to be collected. |  | Accurately and efficiently gather faculty requests for software to be installed in computer labs. | Academic & Faculty Support | Q2 | Small | 2008-11-01 | 2008-12-01 | Hold |  | Information Technology Services | 9: Promote a culture of service excellence at all levels.
140 |  |  | C |  |  | Phased Implementations: - Change Management, Phase II | Next Phases on PMO, QA, Architecture |  | Continuous Service Development | Q2 | Small | 2007-07-01 | 2008-12-01 | Hold | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Information Technology Services | 9: Promote a culture of service excellence at all levels.
141 |  |  | C |  |  | University Directory Improvements | University Directory Improvements | There is a prevailing need to re-design and/or update the “look and feel” of the current University Directory; from the screen design, to the software used to create the screens, to how the data is gathered and managed. Currently, in order to present information for the University Directory, information is retrieved from several locations and manual processes are executed before the data can be accessed through LUC.EDU. Subsequently, it is difficult to keep this information updated and available in a timely manner. | Continuous Service Development | Q2 | Medium | 2007-10-01 | 2008-12-01 | Hold | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Human Resources | 9: Promote a culture of service excellence at all levels.
142 | 626 |  | C |  |  | Resident Parking Lottery Application enhancements |  | Enhancements to Resident Parking Lottery Appl. The initial appl. request was to have a form site for students to apply for access to a parking lot, and an admin site to run a lottery to choose winners for the parking lots based on students' dorm assignment. Enhancement requests include allowing multiple runs of the lottery with different student dorm to parking lot associations. | Academic & Faculty Support | Q2 | Small |  | 2008-12-01 | Hold |  |  | 9: Promote a culture of service excellence at all levels.
143 |  |  | C |  |  | Develop (with Academic Affairs) New Design for Learning Spaces | Develop (with Academic Affairs) New Design for Learning Spaces |  | Academic & Faculty Support | Q3 | X-Large | 2007-09-01 | 2009-01-01 | Active | Lime - On Target, Minimal Risk, Minor Concerns, Under Control | Academic Affairs | 1: Enrich its rigorous academic programs to better integrate the unique strengths and characteristics of a Jesuit and Catholic education.
144 |  |  | C |  |  | Develop and deliver remote technology assistance in use of Blackboard and other teaching technologies for JFRC | Develop and deliver remote technology assistance in use of Blackboard and other teaching technologies for JFRC |  | Academic & Faculty Support | Q4 | Small | 2008-06-01 | 2009-05-01 | Active | Green - On Target, No Risk | Academic Affairs
145 | 656 |  | C |  |  | Enhancements to SCPS Continuum web site - Phase II enhancements |  |  | Academic & Faculty Support | Q4 | Large | 2007-06-01 | 2009-06-01 | Pending |  | AA-Colleges & Schools | 2: Increase its overall student enrollment at the undergraduate and graduate levels through the development of new academic programs.
146 | 541 |  | C |  |  | Provide integrated logon for all Faculty Information Systems modules | Single-sign-on for all Faculty Information Systems modules |  | Continuous Service Development | Q2 | Medium | 2008-02-01 | TBD | Hold |  | AA-Faculty Administration | 9: Promote a culture of service excellence at all levels.
147 | 542 |  | C |  |  | Reformat existing Faculty Information System Modules 1&2 pages to match the updated pages used in the Faculty Development module. | Reformat existing Faculty Information System Modules 1&2 pages to match the updated pages used in the Faculty Development module. |  | Continuous Service Development | Q2 | Medium | 2008-02-01 | TBD | Hold |  | AA-Faculty Administration | 9: Promote a culture of service excellence at all levels.
Note on P82: Bruce Montes: Phase I (install of new release) missed target, which pushed this project out. Project needs redefinition of resources and deliverables. Phase I completed November 2007
Note on P88: Bruce Montes: Costs have been estimated and proposed, but new timeline must be established with Academic Affairs.
Note on P102: Bruce Montes: New Project to replace previous
Note on P109: Bruce Montes: Pace of project is a concern. Resources from all areas required. This project is a partnership with the ATC and the Office for Learning Technologies and Assessment
Note on P110: Bruce Montes: Need to return to PMO process. GA to return in August 2008
Note on P146: Bruce Montes: Is a project and function of the ATS committee. In progress.

## FY08 Q3-Q4 Completed
[6 empty] | Plan of Record Data - Key Fields |  |  |  |  | Plan of Record Data - New Fields
52
Row Nbr | PSS Nbr | Level | Priority | Program Number | Program Group Name | Project Desc | Major Initiative/Ring Desc | Institutional Impact Statement | Strategic Category | Est. Compl. (QTR) | T-Shirt Sizing | Targeted Start Month (MM/YYYY) | Targeted Finish Month (MM/YYYY) | Status | Primary Customer | Goal Alignment
148 | 570 | R | A | 1 | Student System Upgrade | Upgrade the LOCUS Portal to release 8.9 | Student System Upgrade | Continuation of support and regulatory updates for LOCUS after current support ends on 8/31/2007. Required step of the SIS upgrade. | Academic & Faculty Support | Q1 '09 |  | 2007-05-01 | 2008-07-01 | Complete | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
149 | 747 | R | A | 3 | LOCUS Enhancements | Install SA Bundle 21 from PeopleSoft. | LOCUS Enhancements (17) | Regulatory update to SA8.0 Financial Aid update. | Academic & Faculty Support | Q3 | Medium |  | 2008-01-01 | Complete | Academic Affairs | 9: Promote a culture of service excellence at all levels.
150 | 728 | R | A | 3 | LOCUS Enhancements | To identify all of the students with a Study Agreement by study agreement and term who were charged an OIP Administrative Fee. | LOCUS Enhancements (17) | Provide a alert for the office of international program to verify OIP fees | Academic & Faculty Support | Q3 | Medium | 2007-11-13 | 2008-01-30 | Complete | General Accounting | 9: Promote a culture of service excellence at all levels.
151 | 638 | R | A | 3 | LOCUS Enhancements | LOCUS Enhancements: Recording Student Dismissal reasons in LOCUS | LOCUS Enhancements (17) | Collect data on student dismissals. | Administrative Initiatives | Q3 |  | 2007-05-01 | 2008-02-01 | Complete | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
152 | 737 | R | A | 3 | LOCUS Enhancements | Change to Class Search page to remove references to MAGIS and to add a disclaimer statement to the page. | LOCUS Enhancements (17) | Maintain historical reference to MAGIS while removing the MAGIS program. (Program discontinued) | Academic & Faculty Support | Q4 | Medium |  | 2008-04-01 | Complete | AA-Registration & Records | 9: Promote a culture of service excellence at all levels.
153 | 738 | R | A | 3 | LOCUS Enhancements | Transfer Articulation Rules Report for departments and advisors to learn the articulation rules that have been entered in LOCUS. | LOCUS Enhancements (17) | Enhance reports used for department reviews of transfer articulation rules. | Administrative Initiatives | Q1 | X-Small |  | 2008-06-01 | Complete | FN-Parking/Business Services | 9: Promote a culture of service excellence at all levels.
154 | 733 | R | A | 5 | Security Projects | Implement Oracle listener passwords on all oracle servers. | Security Initiatives (PIRG & Audit Related) | Secure databases from external attacks | Infrastructure | Q3 | Small | 2007-11-13 | 2008-03-30 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
155 | 560 | R | A | 7 | BCDR/Failover | BCDR - Web Presence at WTC & LSC | BCDR & Emergency Notification Projects | Fail over of LUC web presence in the event of a campus outage. (Syncing schedule and documentation are all that remain) | Infrastructure | Q3 | Medium |  | 2008-03-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
156 |  | R | A | 7 | BCDR/Failover | BCDR - GroupWise Redesign to provide improved system resiliency in the event of an outage. | BCDR & Emergency Notification Projects | Will allow the university to restore email services by rebuilding services at the opposite campus in the event either campus data center fails. | Infrastructure | Q4 | Medium |  | 2008-06-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
157 | 755 | R | A |  |  | Loyola Alert - Phase I Implement Connect - ED's Emergency Notification System. Provide LDAP authenticated web form for Loyolans to opt in to the emergency notification and enter their preferred contact information. Data will be uploaded daily to Connect-ED. | BCDR & Emergency Notification Projects | Loyola (using Connect-Ed vendor) will provide an opt-in service to contact student/fac/staff in the event of a university emergency. | Infrastructure | Q3 | Medium | 2007-12-01 | 2008-01-01 | Complete | Facilities | 3: Enhance the quality of campus life for resident and commuter students.
158 | 723 | R | A |  |  | Compensation department requests some fixes and new features for Version 5.0 of Staff Salary Planning web application. This application is the tool used to award merit increases and other staff related funds to be incorporated into the annual budgeting process. | Faculty/Staff Salary Planning Enhancements | Implement technical and functional improvements to Staff Salary Planning relating to the correction of rounding issues, enhancements to the data refresh and logging of data for auditing purposes. Project is in final user testing phase. | Administrative Initiatives | Q3 | Medium | 2007-09-01 | 2008-01-01 | Complete | Human Resources | 9: Promote a culture of service excellence at all levels.
159 | 720 | R | A |  |  | Enhancements to Faculty Salary Planning application | Faculty/Staff Salary Planning Enhancements | Implement technical and functional efficiency improvements to Faculty Salary Planning. The modifications focus on data presentation changes and security enhancements. Project is in final user testing phase. | Administrative Initiatives | Q3 | Medium | 2007-09-01 | 2008-01-01 | Complete | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
160 |  | R | A |  |  | Create Mac image for Spring semester | PC/Mac Image for Spring Semester | To provide Mac users with a consistent suite of software applications across the University; initiative driven by curriculum requirements in A&S. | Academic & Faculty Support | Q3 | Large | 2007-02-01 | 2008-01-01 | Complete | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
161 |  | R | A |  |  | Spring PC Image | PC/Mac Image for Spring Semester | Updated lab image based on faculty requests for new software applications. | Academic & Faculty Support | Q3 | Medium | 2007-11-01 | 2008-01-01 | Complete | Academic Affairs | 3: Enhance the quality of campus life for resident and commuter students.
162 | 563 | R | A |  |  | Conference Services - determine and assist in meeting software needs beyond R25/RMS capabilities | Conference Services Enhancements | Enhance conference service capabilities (control over housing room assignments, improved invoicing, integrated space assignments with R25). | Administrative Initiatives | Q3 |  | 2007-09-01 | 2008-03-01 | Complete | FN-Conference Services | 9: Promote a culture of service excellence at all levels.
163 |  | R | A |  |  | Digital Signage - Phase I, Production Implementation | Digital Signage Phase I Rollout | Digital signage technology is needed across the campuses to deliver current event, status, and other Loyola information to the student and university communities in a timely fashion. University Marketing and Communications requires ITS support to deploy a standard digital signage solution in a cost-effective and technically sound manner. Completion of this project will afford the university the ability to deliver timely communications and engage the Loyola community many of the high student traffic areas. | Continuous Service Development | Q3 | Large | 2007-11-01 | 2008-04-01 | Complete | Marketing Communication Services | 3: Enhance the quality of campus life for resident and commuter students.
164 |  |  | A |  |  | Upgrade Blackboard to Bb 8.0 | Upgrade Blackboard to Bb 8.0 | Upgrade to newer version of Blackboard that includes the new Grade Center that offers features requested by faculty and students such as outcome tracking, better reporting and portfolio improvements. | Academic & Faculty Support | Q4 | Small | 2008-03-01 | 2008-05-01 | Complete | Academic Affairs
165 | 750 |  | B | 2 | Credit Card Processing | Credit Card Processing for Beijing Center Reunion |  |  | Administrative Initiatives | Q3 | Medium | 2007-12-01 | 2008-01-01 | Complete | Finance
166 | 751 |  | B | 2 | Credit Card Processing | Credit Card Processing to collect ad revenue for Phoenix Newspaper |  |  | Administrative Initiatives | Q3 | Medium | 2008-01-01 | 2008-03-01 | Complete | Finance
167 | 702 |  | B | 2 | Credit Card Processing | Marketplace store front for Family Business Center - Registration for monthly classes and yearly conference in April |  |  | Administrative Initiatives | Q4 | Medium | 2008-12-01 | 2008-04-01 | Complete | Family Business Center
168 | 748 |  | B | 2 | Credit Card Processing | Credit Card Processing, Career Center Events in Feb, March, and May |  |  | Administrative Initiatives | Q4 |  | 2007-12-01 | 2008-04-01 | Complete | Finance
169 | 703 |  | B | 2 | Credit Card Processing | Credit Card Processing, Discover Loyola | Credit Card Processing |  | Administrative Initiatives | Q4 | Medium | 2008-02-01 | 2008-04-01 | Complete | Finance
170 | 679 | R | B | 3 | LOCUS Enhancements | Academic Progress Units for Dissertation/Thesis Supervision courses | LOCUS Enhancements (17) | Improve institutional data quality by capturing full-time status of students enrolled in designated courses in LOCUS. | Academic & Faculty Support | Q4 |  |  | 2008-04-01 | Complete | AA-Registration & Records
171 |  |  | B | 5 | Security Projects | Long-Term Security Strategy |  | Identify and document the institutional information security risks including risk levels and corresponding action plans. Not having a defined security program will result in an increased risk to the overall information security of the institution. This is due to the inability to properly identify and remdeiate concerns in order of risk. | Continuous Service Development | Q3 | Medium | 2007-09-01 | 2008-02-01 | Complete | Information Technology Services | 3: Enhance the quality of campus life for resident and commuter students.
172 |  | R | B |  |  | Production Implementation of Crestron System | Remote Electronic Classroom Management |  | Academic & Faculty Support | Q2 | Large | 2007-07-01 | 2007-10-01 | Complete | Academic Affairs | 9: Promote a culture of service excellence at all levels.
173 | 707 | R | B |  |  | On-line form & routing for supplementary salary requests for faculty | On-line form & routing for supplementary salary requests for faculty | Reduce the need for routing paper forms, increase efficiency, provide electronic tracking, and reduce clerical errors. | Academic & Faculty Support | Q3 | Medium | 2008-10-01 | 2008-01-01 | Complete | AA-Faculty Administration
174 |  |  | B |  |  | ISP Upgrades at LSC and WTC |  | Will privide additional bandwidth to the Internet. | Infrastructure | Q3 | Small | 2007-08-01 | 2008-01-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
175 |  |  | B |  |  | Intra-campus Videoconferencing Upgrades | Intra-campus Videoconferencing Upgrades | Better communication venue between campuses. | Continuous Service Development | Q3 | Medium | 2007-01-01 | 2008-02-01 | Complete | Office of the President | 6: Promote multidisciplinary collaborations.
176 |  |  | B |  |  | Student Print from Anywhere |  | Improved student service | Continuous Service Development | Q3 |  |  | 2008-03-01 | Complete | Academic Affairs | 3: Enhance the quality of campus life for resident and commuter students.
177 |  |  | B |  |  | Infrastructure in support of Digital Signage |  |  | Continuous Service Development | Q3 |  |  | 2008-03-01 | Complete | Marketing & Communication | 3: Enhance the quality of campus life for resident and commuter students.
178 |  | R | B |  |  | Pilot Crestron RoomView - Remote Management Software | Remote Electronic Classroom Management |  | Academic & Faculty Support | Q4+ |  | 2007-01-01 | 2008-04-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
179 |  | R | B |  |  | Enterprise Imaging Strategy (ECM) | Enterprise Imaging Strategy (ECM) | Identify and document the institutional requirements, needs and corresponding benefits for utilizing an enterprise solution of document imaging and electronic content management. An undocumented strategy will result in unknown or unrealized process improvements, and workflow efficiencies and costs savings. | Administrative Initiatives | Q4 | Large | 2006-12-01 | 2008-05-01 | Complete | AA-Office of the Provost | 9: Promote a culture of service excellence at all levels.
180 |  | R | B |  |  | Bradford Implementation | Replace Computer Registration Process | This registration /authentication system will allow us to manage network access by non-Loyola owned machines. | Student Technology Support | Q3 |  | 2007-06-01 | 2008-05-01 | Complete | Information Technology Services | 3: Enhance the quality of campus life for resident and commuter students.
181 | 717 |  | B |  |  | Web site for students to use to waive out of the required Health Insurance. This would replace the current system which is managed by an outside vendor. This functionality should be available from with the Locus portal after a student has authenticated. |  |  | Administrative Initiatives | Q4 |  | 2008-01-01 | 2008-05-01 | Complete | Office Of The Bursar
182 |  | R | B |  |  | Info Commons Technology Planning - Develop 24-Hour Support Model Proposal - Update Budget Plan for Current Technology | Information Commons |  | Student Technology Support | Q4 | Large | 2008-05-01 | 2008-06-01 | Complete | Student Affairs | 9: Promote a culture of service excellence at all levels.
183 |  |  | B |  |  | Novell Client Upgrade |  | Rollout of new client version to support universal password advanced features | Infrastructure | Q4 | Medium |  | 2008-06-08 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
184 | 601 |  | B |  |  | Continue conversion of LUC web pages to Content Management System | Continue conversion of LUC web pages to Content Management System |  | Continuous Service Development | Q4+ | Medium | 2005-08-01 |  | Complete | Marketing & Communication | 9: Promote a culture of service excellence at all levels.
185 |  |  | C |  |  | Deliver Blackboard Workshops w/Academic Affairs | Deliver Blackboard Workshops w/Academic Affairs |  | Academic & Faculty Support | Q3 | Medium | 2007-01-01 | 2008-01-01 | Complete | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
186 |  |  | C |  |  | GroupWise 7 Client Rollout | GroupWise 7 Rollout | Enhanced client services | Continuous Service Development | Q3 | Medium |  | 2008-03-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
187 |  |  | C |  |  | Lab Machine Background Messaging |  |  | Continuous Service Development | Q3 |  |  | 2008-03-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
188 |  |  | C |  |  | Alumni Machine Library Database Access Policy |  |  | Continuous Service Development | Q4 | Small |  | 2008-06-01 | Complete | Academic Affairs
189 |  | R | M | 4 | Construction Projects | Dumbach Project - Data Center Construction | Move Into Dumbach Data Center | Mandated due to razing of JR. Project will provide a secured and reliable facility for the University's voice and data systems. | Infrastructure | Q3 | X-Large | 2007-05-01 | 2008-01-01 | Complete | Facilities
190 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Info. Commons - Infrastructure Design, Budgeting and Implementation | Campus Construction Initiatives (12) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q3 | Large | 2006-06-01 | 2008-01-01 | Complete | Facilities
191 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Life Sciences - Build out of 7 labs, 4th floor | Campus Construction Initiatives (12) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q3 | Small | 2007-09-15 | 2008-01-01 | Complete | Facilities
192 |  | R | M | 4 | Construction Projects | Construction Initiatives: - Crown Center classrooms, 3 total | Campus Construction Initiatives (12) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q3 | Small | 2007-12-01 | 2008-01-01 | Complete | Facilities
193 |  | R | M | 4 | Construction Projects | Dumbach Project Migrate LSC Telephone Switch to Dumbach | Move Into Dumbach Data Center | Mandated due to razing of JR. Project will provide a secured and reliable facility for the University's voice and data systems. | Infrastructure | Q3 | Large | 2007-09-01 | 2008-03-01 | Complete | Facilities
194 |  | R | M | 4 | Construction Projects | Adding Audio / Visual Infrastructure to Bremner Lounge - Working with ATS | Campus Construction Initiatives (12) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q3 | Small |  | 2008-03-01 | Complete | Facilities
195 |  | R | M | 4 | Construction Projects | Lewis Library remodeling | Campus Construction Initiatives (12) | Mandated. In support of academic and facilities initiatives. | Infrastructure | Q3 | Small | 2007-12-01 | 2008-03-01 | Complete | Facilities
196 |  | R | M | 4 | Construction Projects | Dumbach Project - LSC Plant Cabling Plan and Budget | Move Into Dumbach Data Center | Sub project related to Dumbach data center build out. Required to migrate all cabling from JR to Dumbach. | Infrastructure | Q4+ | X-Large | 2007-09-01 | 2008-05-01 | Complete | Information Technology Services | 9: Promote a culture of service excellence at all levels.
197 |  | R | M |  |  | Addition of 30 Electronic Classrooms | Remote Electronic Classroom Management | In support of academic and facilities initiatives, ITS coordinates, installs, and supports new classrooms defined in construction projects. New classrooms in the Mundelein Center and the Crown Center are being developed for the start of the spring ’08 semester. | Academic & Faculty Support | Q3 | Medium | 2007-05-01 | 2008-01-01 | Complete | Academic Affairs | 5: Improve the academic quality of incoming students and academic programs.
198 |  |  | M |  |  | Identifying avenues to broadcast athletic events from various sporting venues |  | Promotion of athletic programs | Continuous Service Development | Q4 | Small | 2007-12-01 | 2008-05-01 | Complete | Student Affairs
199 |  |  | M |  |  | Construction Initiatives: - Jesuit Residence demolition | Campus Construction Initiatives (12) | Relocate occupants and prepare Jesuit Residence for demolition | Infrastructure |  | Medium | 2008-04-01 | 2008-05-01 | Complete | Facilities